## Requirement_Matrix
req_id | feature_id | domain | feature | evidence_class | sources | disposition | release | screens | calculations | connectors | work_package | owner_role | acceptance | note
REQ-001 | F-A01 | A | Login with MFA (authenticator app, e-mail), session policy | OBS | S17,OBS | IN | R0 | SCR-001 |  |  | WP-03 | Backend lead | Given synthetic fixture FIX-A-001 for SCR-001, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-001), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-002 | F-A02 | A | Multi-workspace / multi-account switcher | OBS | OBS | IN | R0 | SCR-002 |  |  | WP-04 | Backend | Given synthetic fixture FIX-A-002 for SCR-002, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-002), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-003 | F-A03 | A | Legal entities, brands, stores, marketplaces, warehouses config | PROP | OBS | IN | R0 | SCR-115,SCR-101 |  |  | WP-04 | Backend | Given synthetic fixture FIX-A-003 for SCR-115,SCR-101, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-115,SCR-101), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Marketplaces from the v0.3 marketplace master (F-A11)
REQ-004 | F-A04 | A | Currencies, timezones, target periods per store | OBS | OBS | IN | R0 | SCR-101 | CALC-026 |  | WP-04 | Backend | Given synthetic fixture FIX-A-004 for SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-033 to the cent.
REQ-005 | F-A05 | A | Summary dashboard across accounts | OBS | OBS,S11 | IN | R2 | SCR-003 | CALC-013,CALC-051,CALC-101 |  | WP-08 | Frontend | Given synthetic fixture FIX-A-005 for SCR-003, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-015, GV-046, GV-074, GV-114, GV-139 to the cent.
REQ-006 | F-A06 | A | User invitations & roles by function/product/market | OBS | S03,PROP | IN | R0 | SCR-115 |  |  | WP-03 | Backend lead | Given synthetic fixture FIX-A-006 for SCR-115, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-115), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Sellerboard gates users by plan; internal app: RBAC
REQ-007 | F-A07 | A | Safe demo mode (synthetic data) | OBS | OBS | IN | R0 | SCR-002 |  |  | WP-03 | Backend lead | Given synthetic fixture FIX-A-007 for SCR-002, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-002), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-008 | F-A08 | A | Data retention & lifecycle settings | OBS | OBS,S24 | IN | R0 | SCR-101 |  |  | WP-06 | Backend | Given synthetic fixture FIX-A-008 for SCR-101, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-101), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-009 | F-A09 | A | Personalization: dark/light, remembered views, column pickers | OBS | OBS | IN | R1 | SCR-010 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-A-009 for SCR-010, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-010), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-010 | F-B01 | B | Profit tiles Today/Yesterday/MTD/Forecast/Last month with comparisons | OBS | OBS | IN | R1 | SCR-010,SCR-016 | CALC-002,CALC-013,CALC-045,CALC-108 | CON-01 | WP-08 | Frontend | Given synthetic fixture FIX-B-010 for SCR-010,SCR-016, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-002, GV-003, GV-015, GV-030, GV-045, GV-046, GV-146 to the cent.
REQ-011 | F-B02 | B | Tile 'More' P&L drilldown (expandable lines, fee breakdown) | OBS | OBS | IN | R1 | SCR-011 | CALC-001,CALC-003,CALC-010,CALC-012,CALC-015,CALC-019,CALC-050,CALC-051,CALC-052 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-011 for SCR-011, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-001, GV-004, GV-011, GV-014, GV-053, GV-054, GV-058, GV-067, GV-068, GV-073, GV-074, GV-075, GV-076, GV-143 to the cent.
REQ-012 | F-B03 | B | Chart view (units/ads/refunds/net profit) with configuration | OBS | OBS | IN | R1 | SCR-012 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-B-012 for SCR-012, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-012), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-013 | F-B04 | B | P&L table by day/month with heatmap and compare/YoY | OBS | OBS,S13,S18 | IN | R1 | SCR-013 | CALC-013,CALC-050,CALC-051,CALC-108 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-013 for SCR-013, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-015, GV-046, GV-073, GV-074, GV-075, GV-146 to the cent.
REQ-014 | F-B05 | B | Trends per product per metric with forecast column | OBS | OBS,S12 | IN | R1 | SCR-015 | CALC-030,CALC-031,CALC-108 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-014 for SCR-015, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-047, GV-048, GV-141, GV-146 to the cent.
REQ-015 | F-B06 | B | Map / region view (sales, stock) | OBS | OBS | IN | R2 | SCR-014 | CALC-111 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-015 for SCR-014, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-149 to the cent.
REQ-016 | F-B07 | B | Products/Order-items tables with group-by, search, sort, column picker, export | OBS | OBS | IN | R1 | SCR-010,SCR-017 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-B-016 for SCR-010,SCR-017, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-010,SCR-017), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-017 | F-B08 | B | Custom dashboard tiles (up to 8 metrics) | DOC | S18 | IN | R1 | SCR-016 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-B-017 for SCR-016, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-016), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-018 | F-B09 | B | Targets, ASP, AOV, sessions/conversion, payout estimate | OBS+PROP | OBS,S14 | IN | R1 | SCR-010 | CALC-014,CALC-016,CALC-017,CALC-018,CALC-048,CALC-053,CALC-054 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-018 for SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-017, GV-019, GV-055, GV-056, GV-057, GV-064, GV-077, GV-078, GV-135 to the cent.
REQ-019 | F-B10 | B | Amazon / Shopify / other-channel dashboard views | DOC | S01,S03,S09 | IN | R2 | SCR-090 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-B-019 for SCR-090, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-090), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-020 | F-B11 | B | Dashboard currency switch | OBS | OBS | IN | R2 | SCR-010 | CALC-026,CALC-081 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-020 for SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-033, GV-121 to the cent.
REQ-021 | F-C01 | C | COGS policies: fixed, percentage, by period, batch, FIFO, weighted average | OBS | OBS,S01,S13 | IN | R1 | SCR-021 | CALC-005,CALC-006,CALC-007,CALC-078 |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-021 for SCR-021, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-006, GV-007, GV-008, GV-009, GV-010, GV-018, GV-069, GV-072, GV-102 to the cent.
REQ-022 | F-C02 | C | FIFO oversold policy (last batch / zero / fixed) + alert | OBS | OBS,S13,S18 | IN | R1 | SCR-021,SCR-101 | CALC-007 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-C-022 for SCR-021,SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-008, GV-009, GV-010, GV-072 to the cent.
REQ-023 | F-C03 | C | Landed-cost elements per batch | OBS | OBS | IN | R1 | SCR-022 | CALC-008 |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-023 for SCR-022, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-012, GV-013 to the cent.
REQ-024 | F-C04 | C | SKU/ASIN/variant mapping, multi-channel COGS tab | OBS | OBS | IN | R1 | SCR-020,SCR-021 | CALC-066,CALC-087 |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-024 for SCR-020,SCR-021, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-089, GV-127 to the cent.
REQ-025 | F-C05 | C | Bundles / BOM | PROP | PROP | IN | R2 | SCR-024 | CALC-005 |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-025 for SCR-024, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-006, GV-018, GV-069 to the cent.
REQ-026 | F-C06 | C | COGS import/export (CSV/XLSX), multi-product batch | OBS | OBS | IN | R1 | SCR-023 |  |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-026 for SCR-023, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-023), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-027 | F-C07 | C | Recurring COGS feed from Google Sheets / URL (daily) | DOC | S12 | IN | R1 | SCR-025 | CALC-087 | CON-23 | WP-09 | Full-stack | Given synthetic fixture FIX-C-027 for SCR-025, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-127 to the cent. | COGS import by SKU/EAN/UPC added by vendor 2026-10-08
REQ-028 | F-C08 | C | Missing/zero COGS detection and alert | DOC | S18 | IN | R1 | SCR-076 | CALC-043 |  | WP-34 | Financial/data eng | Given synthetic fixture FIX-C-028 for SCR-076, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-044 to the cent.
REQ-029 | F-C09 | C | Cost-change history, preview, closed-period effect | PROP | PROP | IN | R1 | SCR-021 | CALC-024 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-C-029 for SCR-021, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-025, GV-026 to the cent.
REQ-030 | F-D01 | D | Marketplace fee taxonomy incl. India-specific (TDS, affordability, technology, closing) & unknown codes | OBS | OBS,S03 | IN | R1 | SCR-032,SCR-011 | CALC-003,CALC-067,CALC-109 | CON-01 | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-030 for SCR-032,SCR-011, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-004, GV-011, GV-091, GV-147 to the cent.
REQ-031 | F-D02 | D | Refunds: partial, refund-without-return, unsellable, fee/tax reversals | OBS | OBS,S17 | IN | R1 | SCR-034 | CALC-004,CALC-009,CALC-053,CALC-054,CALC-082 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-031 for SCR-034, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-005, GV-016, GV-077, GV-078, GV-122, GV-138 to the cent. | FBM refund reasons added by vendor 2026-09-10
REQ-032 | F-D03 | D | Actual vs estimated shipping; ShipStation actuals | DOC | S01,S49 | IN | R1 | SCR-033 | CALC-020 | CON-32 | WP-13 | Financial/data eng | Given synthetic fixture FIX-D-032 for SCR-033, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-022, GV-023, GV-137 to the cent. | R1 uses courier/3PL actuals (CON-32, WP-35); ShipStation actuals (CON-20) arrive with WP-39 in R5
REQ-033 | F-D04 | D | Shipping profiles (zones/weight/value/units); highest-vs-sum mixed orders | OBS | OBS,S01,S14 | IN | R1 | SCR-033,SCR-101 | CALC-020 |  | WP-13 | Financial/data eng | Given synthetic fixture FIX-D-033 for SCR-033,SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-022, GV-023, GV-137 to the cent.
REQ-034 | F-D05 | D | Pick & pack per order/item, first-X-items rate | OBS | OBS,S01 | IN | R1 | SCR-033,SCR-101 | CALC-021 |  | WP-13 | Financial/data eng | Given synthetic fixture FIX-D-034 for SCR-033,SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-024 to the cent.
REQ-035 | F-D06 | D | Gateway / POS / payment fees | DOC | S01 | IN | R1 | SCR-033 | CALC-022 | CON-06 | WP-13 | Financial/data eng | Given synthetic fixture FIX-D-035 for SCR-033, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-020, GV-021, GV-136 to the cent. | Other gateways (CON-07) by CSV in R1; gateway connectors in R2
REQ-036 | F-D07 | D | Indirect expenses: one-off/recurring/daily; multi-marketplace; tag/SKU | OBS | OBS,S16 | IN | R1 | SCR-030 | CALC-024 |  | WP-10 | Full-stack | Given synthetic fixture FIX-D-036 for SCR-030, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-025, GV-026 to the cent.
REQ-037 | F-D08 | D | Variable / tag-based expenses with conditions and validity | OBS | OBS,S16 | IN | R1 | SCR-031 | CALC-011,CALC-091 |  | WP-10 | Full-stack | Given synthetic fixture FIX-D-037 for SCR-031, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-066, GV-131 to the cent.
REQ-038 | F-D09 | D | Fee amortization (daily) for storage/inbound/removal etc. | OBS | OBS,S15 | IN | R1 | SCR-101 | CALC-024 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-038 for SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-025, GV-026 to the cent.
REQ-039 | F-D10 | D | Cross-market allocations & conservation | PROP | PROP | IN | R1 | SCR-030 | CALC-023 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-039 for SCR-030, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-027 to the cent.
REQ-040 | F-D11 | D | GST/TCS/VAT recoverability & marketplace-facilitator split | OBS | OBS,S18 | IN | R1 | SCR-101 | CALC-025 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-040 for SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-028, GV-029, GV-145 to the cent.
REQ-041 | F-E01 | E | PPC dashboard portfolio→campaign→ad group→keyword→search term with profit & break-even ACOS | OBS | OBS,S04 | OMITTED | R4 | SCR-040 | CALC-028,CALC-029 | CON-02 |  |  | Given synthetic fixture FIX-E-041 for SCR-040, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-059, GV-060 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-042 | F-E02 | E | Real ACOS / TACOS product-scoped on trends | OBS | OBS,S12 | IN | R1 | SCR-015 | CALC-030,CALC-031 |  | WP-08 | Frontend | Given synthetic fixture FIX-E-042 for SCR-015, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-047, GV-048, GV-141 to the cent.
REQ-043 | F-E03 | E | Bid recommendations, harvesting, negatives, budget adjustments, isolation | OBS | OBS,S04 | OMITTED | R4 | SCR-041 | CALC-088,CALC-112 | CON-26 |  |  | Given synthetic fixture FIX-E-043 for SCR-041, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-128, GV-150 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-044 | F-E04 | E | Automation: manual approval / autopilot; day parting (beta) | OBS | OBS,S04 | OMITTED | R4 | SCR-047,SCR-042 |  | CON-26 |  |  | Given synthetic fixture FIX-E-044 for SCR-047,SCR-042, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-047,SCR-042), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-045 | F-E05 | E | Automation log completed/pending (repricer writes only) | OBS | OBS | IN | R4 | SCR-042 |  |  | WP-20 | Backend | Given synthetic fixture FIX-E-045 for SCR-042, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-042), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-046 | F-E06 | E | External ads (Google/Meta/TikTok/Snap/Pinterest/Taboola) spend + UTM/session attribution | DOC | S01,S02 | OMITTED | R5 | SCR-043 | CALC-032 | CON-08..CON-14 |  |  | Given synthetic fixture FIX-E-046 for SCR-043, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-049 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-047 | F-E07 | E | Amazon Attribution external traffic | DOC | S12 | OMITTED | R2 | SCR-044 | CALC-032 | CON-04 |  |  | Given synthetic fixture FIX-E-047 for SCR-044, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-049 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-048 | F-E08 | E | Search-term performance (Brand Analytics) | DOC | S05,S16 | OMITTED | R4 | SCR-045 | CALC-074 | CON-03 |  |  | Given synthetic fixture FIX-E-048 for SCR-045, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-099 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-049 | F-E09 | E | Keyword research | OBS | OBS,S06 | OMITTED | R4 | SCR-046 |  | CON-03 |  |  | Given synthetic fixture FIX-E-049 for SCR-046, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-046), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-050 | F-E10 | E | Product/ad mapping & organic vs paid split | OBS | OBS | OMITTED | R4 | SCR-040 | CALC-031,CALC-049 |  |  |  | Given synthetic fixture FIX-E-050 for SCR-040, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-047, GV-070 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-051 | F-E11 | E | First-party cookie / Shopify customerJourneySummary attribution | DOC | S01,S20 | OMITTED | R2 | SCR-043 | CALC-032 | CON-05 |  |  | Given synthetic fixture FIX-E-051 for SCR-043, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-049 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-052 | F-F01 | F | LTV per buyer (sales, units, orders) 3/6/12/24 months, per product | OBS | OBS,S01 | IN | R2 | SCR-050 | CALC-033 |  | WP-14 | Data eng | Given synthetic fixture FIX-F-052 for SCR-050, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-035, GV-036 to the cent.
REQ-053 | F-F02 | F | Cohorts, retention, repeat rate, time-to-second purchase, CAC, payback with maturity flags | PROP | S01,PROP | IN | R2 | SCR-051 | CALC-034,CALC-035,CALC-036 |  | WP-14 | Data eng | Given synthetic fixture FIX-F-053 for SCR-051, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-037, GV-061, GV-062, GV-065, GV-071 to the cent.
REQ-054 | F-F03 | F | Repeat customers report (by brand) | OBS | OBS | IN | R2 | SCR-052 | CALC-035,CALC-083 |  | WP-11 | Backend | Given synthetic fixture FIX-F-054 for SCR-052, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-037, GV-123 to the cent.
REQ-055 | F-F04 | F | Subscription contracts vs repeat orders (SnS count observed) | OBS | OBS,S20 | CONDITIONAL | R2 | SCR-051 |  | CON-29 | WP-14 | Data eng | Given synthetic fixture FIX-F-055 for SCR-051, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-051), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | No cross-app contract read on Shopify
REQ-056 | F-G01 | G | Inventory by warehouse / fulfillment mode; reserved, saleable, damaged, prep, inbound, ordered | OBS | OBS | IN | R3 | SCR-060 | CALC-040 | CON-01 | WP-15 | Full-stack | Given synthetic fixture FIX-G-056 for SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-052 to the cent.
REQ-057 | F-G02 | G | Stock value & age, velocity, days of cover, safety stock, lead time | OBS+PROP | OBS,S13 | IN | R3 | SCR-060 | CALC-037,CALC-038 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-057 for SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-039, GV-063, GV-133 to the cent.
REQ-058 | F-G03 | G | Reorder alerts / action-required with funds needed & profit at risk | OBS | OBS,S13 | IN | R3 | SCR-060 | CALC-039 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-058 for SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-038, GV-134 to the cent.
REQ-059 | F-G04 | G | Purchase orders (draft/ordered/shipped), suppliers (multi-currency), receiving, MOQ/carton | OBS+PROP | OBS | IN | R3 | SCR-061,SCR-062 | CALC-039 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-059 for SCR-061,SCR-062, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-038, GV-134 to the cent.
REQ-060 | F-G05 | G | FBA / inbound shipment tracking, % received, discrepancies | OBS | OBS | IN | R3 | SCR-063 |  | CON-01 | WP-15 | Full-stack | Given synthetic fixture FIX-G-060 for SCR-063, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-063), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-061 | F-G06 | G | Prep-center stock auto-reduction on inbound | OBS | OBS | IN | R3 | SCR-101 | CALC-040 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-061 for SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-052 to the cent.
REQ-062 | F-G07 | G | Stock history report & reconciliation, shrinkage | OBS+PROP | OBS | IN | R3 | SCR-064 | CALC-040 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-062 for SCR-064, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-052 to the cent.
REQ-063 | F-G08 | G | Reseller / sourcing workflow (mobile scan, FNSKU labels) | DOC | S08 | CONDITIONAL | R5 | SCR-065 |  | CON-01 | WP-24 | Frontend | Given synthetic fixture FIX-G-063 for SCR-065, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-065), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Native app needs explicit scope
REQ-064 | F-H01 | H | Lost & damaged reimbursement candidates (estimate, report) | OBS | OBS | IN | R3 | SCR-070 | CALC-044 | CON-01 | WP-16 | Full-stack | Given synthetic fixture FIX-H-064 for SCR-070, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-050 to the cent.
REQ-065 | F-H02 | H | Returns not received / refund-without-return candidates | OBS | OBS | IN | R3 | SCR-071 | CALC-044 | CON-01 | WP-16 | Full-stack | Given synthetic fixture FIX-H-065 for SCR-071, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-050 to the cent.
REQ-066 | F-H03 | H | FBA fee-change (weight/dimension) candidates | OBS | OBS | IN | R3 | SCR-072 |  | CON-01 | WP-16 | Full-stack | Given synthetic fixture FIX-H-066 for SCR-072, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-072), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-067 | F-H04 | H | Claim tracker: eligibility, deadlines, policy version, evidence, appeals, realized credits | PROP | PROP | IN | R3 | SCR-073 | CALC-044 |  | WP-16 | Full-stack | Given synthetic fixture FIX-H-067 for SCR-073, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-050 to the cent. | No claims-submission API assumed
REQ-068 | F-H05 | H | Review request campaigns: eligibility, targeting, schedules, dedup, per-order status | OBS | OBS,S07,S31 | OMITTED | R3 | SCR-074,SCR-075 | CALC-042 | CON-24 |  |  | Given synthetic fixture FIX-H-068 for SCR-074,SCR-075, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-042, GV-043 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-069 | F-H06 | H | Alerts: listing/Buy Box/seller count/fee/feedback/stock/ad-spend missing or spike/inbound; priorities; routing; resolution (no PPC recommendation alerts) | OBS | OBS,S03 | IN | R3 | SCR-076,SCR-077 | CALC-043 |  | WP-17 | Backend | Given synthetic fixture FIX-H-069 for SCR-076,SCR-077, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-044 to the cent. | vendor added weekly FNSKU low-inventory-fee alerts 2026-09-23
REQ-070 | F-H07 | H | Alert notification channels (in-app, e-mail, per-recipient) & escalation | OBS | OBS | IN | R3 | SCR-077 |  |  | WP-17 | Backend | Given synthetic fixture FIX-H-070 for SCR-077, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-077), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-071 | F-I01 | I | Repricer strategy profiles (max profit/sales/liquidation), min/max by ROI/margin/COGS+%, floor, overrides | DOC | S10 | CONDITIONAL | R4 | SCR-080 | CALC-041 | CON-25 | WP-22 | Full-stack | Given synthetic fixture FIX-I-071 for SCR-080, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-040, GV-041 to the cent. | Not visible in audited accounts; write requires approval
REQ-072 | F-I02 | I | Guardrails: marketplace bounds, ±% caps, stale-data stop, kill switch, simulation, approval | DOC | S10,PROP | CONDITIONAL | R4 | SCR-080,SCR-047 | CALC-041,CALC-075 |  | WP-20 | Backend | Given synthetic fixture FIX-I-072 for SCR-080,SCR-047, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-040, GV-041, GV-100 to the cent. | vendor added Was-price cap and private-label velocity mode 2026-09-28
REQ-073 | F-I03 | I | Price history, Buy Box observations, change log, provider-result audit | DOC | S10 | IN | R4 | SCR-081 |  | CON-01 | WP-22 | Full-stack | Given synthetic fixture FIX-I-073 for SCR-081, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-081), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-074 | F-J01 | J | Walmart / WFS / Connect / SEM views, Walmart-only summary | DOC | S09,S11,S14 | IN | R2 | SCR-090 |  | CON-16 | WP-23 | Integration eng | Given synthetic fixture FIX-J-074 for SCR-090, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-090), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-075 | F-J02 | J | eBay dashboard, LTV, products, orders, expenses; order-level COGS import | OBS | OBS,S11,S18 | IN | R2 | SCR-090 |  | CON-17 | WP-23 | Integration eng | Given synthetic fixture FIX-J-075 for SCR-090, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-090), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | vendor added eBay bulk hide 2026-09-10
REQ-076 | F-J03 | J | TikTok Shop (commerce) distinct from TikTok Ads | DOC | S02 | IN | R2 | SCR-090 |  | CON-18 | WP-23 | Integration eng | Given synthetic fixture FIX-J-076 for SCR-090, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-090), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | TikTok Shop commerce only; TikTok Ads omitted (marketing)
REQ-077 | F-J04 | J | Multichannel fulfillment order filtering & economic dedup (MCF/WFS) | OBS | OBS,S11 | IN | R2 | SCR-091,SCR-101 | CALC-047 |  | WP-13 | Financial/data eng | Given synthetic fixture FIX-J-077 for SCR-091,SCR-101, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-031, GV-032, GV-140 to the cent.
REQ-078 | F-J05 | J | Amazon→Shopify listing / MCF connector (historical claim) | HIST | S19,OBS | CONDITIONAL | R5 | SCR-100 |  | CON-05 | WP-23 | Integration eng | Given synthetic fixture FIX-J-078 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Settings section observed; availability of listing/MCF functions UNVERIFIED; v0.3: not scheduled in WP-23 work — needs its own change request
REQ-079 | F-B12 | B | Unified dashboard: Amazon + Shopify + B2B in one tiles/chart/P&L/trends view with channel, account and entity filters | OBS+PROP | OBS,S41 | IN | R1 | SCR-120,SCR-010 | CALC-101,CALC-050,CALC-051 | CON-01,CON-05 | WP-32 | Financial/data eng | Given synthetic fixture FIX-B-079 for SCR-120,SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-073, GV-074, GV-075, GV-114, GV-139 to the cent. | User requirement 2026-10-10
REQ-080 | F-B13 | B | Sellerboard-compatible P&L mode (same line names, order and definitions) with contribution-margin toggle | OBS-R | OBS | IN | R1 | SCR-011,SCR-013 | CALC-050,CALC-051,CALC-052 |  | WP-34 | Financial/data eng | Given synthetic fixture FIX-B-080 for SCR-011,SCR-013, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-073, GV-074, GV-075, GV-076 to the cent. | Formulas reconciled against authorized session
REQ-081 | F-B14 | B | Calculation lineage drawer and data freshness/completeness indicators | PROP | PROP | IN | R1 | SCR-129,SCR-130 |  |  | WP-34 | Financial/data eng | Given synthetic fixture FIX-B-081 for SCR-129,SCR-130, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-129,SCR-130), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-082 | F-B15 | B | Targets and budget vs actual by channel/entity | PROP | PROP | IN | R2 | SCR-131 | CALC-107 |  | WP-36 | Financial/data eng | Given synthetic fixture FIX-B-082 for SCR-131, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-120 to the cent.
REQ-083 | F-B16 | B | Parallel-run reconciliation against Sellerboard exports during migration | PROP | PROP | IN | R1 | SCR-114 | CALC-051 |  | WP-34 | Financial/data eng | Given synthetic fixture FIX-B-083 for SCR-114, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-074 to the cent.
REQ-084 | F-B17 | B | SnS penetration and BSR snapshot | DOC | OBS,help | IN | R1 | SCR-010 | CALC-072,CALC-085 | CON-01 | WP-08 | Frontend | Given synthetic fixture FIX-B-084 for SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-097, GV-125 to the cent.
REQ-085 | F-C10 | C | COGS variants: tiered quantity cost, % of list/selling price, shared COGS master across channels | OBS | OBS | IN | R1 | SCR-021,SCR-020 | CALC-078,CALC-087 |  | WP-09 | Full-stack | Given synthetic fixture FIX-C-085 for SCR-021,SCR-020, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-102, GV-127 to the cent.
REQ-086 | F-C11 | C | Closing a purchase order creates a cost batch with freight allocation | DOC | blog 2026-10-02 | IN | R3 | SCR-061 | CALC-086 |  | WP-15 | Full-stack | Given synthetic fixture FIX-C-086 for SCR-061, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-126 to the cent.
REQ-087 | F-C12 | C | Grade & Resell COGS double-count guard | DOC | help | IN | R1 | SCR-021 | CALC-080 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-C-087 for SCR-021, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-104 to the cent.
REQ-088 | F-D12 | D | Shopify revenue composition: gross sales, discounts, shipping charged, refunds, tips, chargebacks, gift cards | OBS-R | OBS | IN | R1 | SCR-011,SCR-120 | CALC-076,CALC-052 | CON-05 | WP-13 | Financial/data eng | Given synthetic fixture FIX-D-088 for SCR-011,SCR-120, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-076, GV-090 to the cent.
REQ-089 | F-D13 | D | Payment fees per gateway (platform fee + gateway % + fixed; Auto actual) | OBS | OBS | IN | R1 | SCR-135 | CALC-022 | CON-05,CON-06 | WP-35 | Integration eng | Given synthetic fixture FIX-D-089 for SCR-135, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-020, GV-021, GV-136 to the cent.
REQ-090 | F-D14 | D | Return shipping, return processing and country surcharge | OBS | OBS | IN | R1 | SCR-033 | CALC-077 |  | WP-35 | Integration eng | Given synthetic fixture FIX-D-090 for SCR-033, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-101 to the cent.
REQ-091 | F-D15 | D | Order inclusion rules (status/channel/tag) and COD/RTO cost handling | OBS+PROP | OBS | IN | R1 | SCR-136 | CALC-090,CALC-104 | CON-05 | WP-35 | Integration eng | Given synthetic fixture FIX-D-091 for SCR-136, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-118, GV-130 to the cent. | India COD/RTO not handled by vendor
REQ-092 | F-D16 | D | Actual courier/3PL fulfilment cost import replacing profile estimates | PROP | OBS | CONDITIONAL | R1 | SCR-033,SCR-136 | CALC-105 | CON-32 | WP-35 | Integration eng | Given synthetic fixture FIX-D-092 for SCR-033,SCR-136, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-117 to the cent. | Observed: Shopify shipping profile mirrors customer-charged amount; pick&pack zero
REQ-093 | F-D17 | D | Advertising cost composition incl. flagged expenses and local GST on ads | OBS | OBS,help | IN | R1 | SCR-011 | CALC-079 |  | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-093 for SCR-011, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-103, GV-155 to the cent.
REQ-094 | F-D18 | D | Fee allocation: inbound by volume/weight; account-level fees by driver | DOC | help | IN | R1 | SCR-032 | CALC-067 | CON-01 | WP-07 | Financial/data eng | Given synthetic fixture FIX-D-094 for SCR-032, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-091 to the cent.
REQ-095 | F-E12 | E | Dual attribution: platform-reported vs first/last-visit attributed, customer journey | OBS-R | OBS | OMITTED | R2 | SCR-133,SCR-134 | CALC-061,CALC-056 | CON-05,CON-08,CON-09 |  |  | Given synthetic fixture FIX-E-095 for SCR-133,SCR-134, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-080, GV-093, GV-151 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-096 | F-E13 | E | PPC profit, unit metrics and break-even bid | OBS-R | OBS,help | OMITTED | R4 | SCR-040 | CALC-055,CALC-056,CALC-057,CALC-049 | CON-02 |  |  | Given synthetic fixture FIX-E-096 for SCR-040, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-070, GV-079, GV-080, GV-081 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-097 | F-E14 | E | Day parting (heatmap read; bid writes conditional) | DOC | blog 2026-10-08,OBS | OMITTED | R4 | SCR-041,SCR-047 | CALC-058 | CON-26 |  |  | Given synthetic fixture FIX-E-097 for SCR-041,SCR-047, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-082 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-098 | F-E15 | E | Blended ROAS, POAS, MER | OBS-R | OBS | IN | R1 | SCR-120,SCR-010 | CALC-059 |  | WP-08 | Frontend | Given synthetic fixture FIX-E-098 for SCR-120,SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-083 to the cent.
REQ-099 | F-E16 | E | Amazon Attribution campaign-level profit | DOC | blog 2026-09-10 | OMITTED | R2 | SCR-044 | CALC-060 | CON-04 |  |  | Given synthetic fixture FIX-E-099 for SCR-044, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-084 to the cent. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-100 | F-F05 | F | Trailing-window LTV set (3/6/12/24 and 12–48 months) incl. profit per customer, repurchase rate, days between orders, CAC, ROAS, POAS | OBS | OBS | IN | R2 | SCR-050 | CALC-084 | CON-05 | WP-14 | Data eng | Given synthetic fixture FIX-F-100 for SCR-050, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-124 to the cent.
REQ-101 | F-F06 | F | Replenishment cycle tracking for cartridges/candles with due list | PROP | PROP | IN | R2 | SCR-132 | CALC-106 | CON-05 | WP-14 | Data eng | Given synthetic fixture FIX-F-101 for SCR-132, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-119 to the cent. | Business-specific improvement
REQ-102 | F-G09 | G | Weighted velocity, seasonality, lead-time components, days until next order, stock value/potential, missed profit, profit forecast | OBS-R | OBS | IN | R3 | SCR-060,SCR-137 | CALC-037,CALC-038,CALC-039,CALC-062,CALC-063,CALC-064,CALC-065,CALC-089 |  | WP-15 | Full-stack | Given synthetic fixture FIX-G-102 for SCR-060,SCR-137, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-038, GV-039, GV-063, GV-085, GV-086, GV-087, GV-088, GV-129, GV-133, GV-134, GV-142 to the cent.
REQ-103 | F-G10 | G | Multi-location stock (3PL warehouses, factory, FBA) with shared stock pools | OBS | OBS | IN | R3 | SCR-060 | CALC-092 | CON-05 | WP-15 | Full-stack | Given synthetic fixture FIX-G-103 for SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-132 to the cent.
REQ-104 | F-H10 | H | Reimbursement gap, fee-change overcharge, refund-without-return and lost/damaged estimates | DOC | help | IN | R3 | SCR-070,SCR-071,SCR-072 | CALC-068,CALC-069,CALC-070,CALC-071 | CON-01 | WP-16 | Full-stack | Given synthetic fixture FIX-H-104 for SCR-070,SCR-071,SCR-072, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-092, GV-094, GV-095, GV-096 to the cent.
REQ-105 | F-H11 | H | Low-inventory-level fee risk alert (weekly, FNSKU) | DOC | blog 2026-09-23 | IN | R3 | SCR-076 | CALC-043 | CON-01 | WP-17 | Backend | Given synthetic fixture FIX-H-105 for SCR-076, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-044 to the cent.
REQ-106 | F-M01 | M | B2B customer master: distributor/dealer/institution/intercompany, GSTIN, place of supply, terms & limit, price list, salesperson/territory | PROP | R-B2B | IN | R1 | SCR-122 |  |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-106 for SCR-122, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-122), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-107 | F-M02 | M | Manual B2B invoice entry with product master lines, HSN, auto GST split, freight, warehouse/batch; draft → approved → posted (maker-checker) | PROP | R-B2B | IN | R1 | SCR-123 | CALC-093,CALC-094,CALC-095,CALC-096 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-107 for SCR-123, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-105, GV-106, GV-107, GV-108, GV-109 to the cent.
REQ-108 | F-M03 | M | Credit notes, returns, schemes and rebates | PROP | R-B2B | IN | R1 | SCR-124 | CALC-095,CALC-097 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-108 for SCR-124, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-108, GV-110 to the cent.
REQ-109 | F-M04 | M | B2B bulk import (CSV/XLSX) with validation and duplicate detection; accounting export | PROP | R-B2B | IN | R1 | SCR-126 | CALC-100 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-109 for SCR-126, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-113 to the cent. | R1 accounting export is a file (CSV/XLSX); the accounting API connector CON-27 is R5
REQ-110 | F-M05 | M | Receivables & collections: receipts, TDS withheld, aging, MSME 45-day flag, DSO, overdue alerts | PROP | R-B2B | IN | R2 | SCR-125 | CALC-098 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-110 for SCR-125, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-111 to the cent.
REQ-111 | F-M06 | M | Export invoices (LUT, currency, shipping bill, realisation deadline) | PROP | R-B2B | IN | R2 | SCR-123 | CALC-099,CALC-026 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-111 for SCR-123, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-033, GV-112 to the cent.
REQ-112 | F-M07 | M | B2B in unified dashboard by customer/territory/salesperson with contribution and intercompany elimination | PROP | R-B2B | IN | R1 | SCR-120,SCR-121,SCR-127 | CALC-097,CALC-100,CALC-101,CALC-110 |  | WP-32 | Financial/data eng | Given synthetic fixture FIX-M-112 for SCR-120,SCR-121,SCR-127, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-110, GV-113, GV-114, GV-139, GV-148 to the cent.
REQ-113 | F-M08 | M | Tax masters (HSN/GST rates, LUT, e-invoice/e-way bill settings) and read-only compliance flags | PROP | R-B2B | IN | R1 | SCR-128 | CALC-102 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-113 for SCR-128, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-115, GV-144 to the cent. | No filing or IRN generation in scope
REQ-114 | F-M09 | M | Stock deduction on B2B dispatch shared with Shopify/3PL/FBA pools without double count | PROP | R-B2B | IN | R2 | SCR-060 | CALC-092,CALC-096 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-114 for SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-109, GV-132 to the cent.
REQ-115 | F-M10 | M | Salesperson commission, price realisation, expected-credit-loss provision | PROP | R-B2B | IN | R2 | SCR-127 | CALC-103 |  | WP-31 | Full-stack | Given synthetic fixture FIX-M-115 for SCR-127, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-116 to the cent.
REQ-116 | F-M11 | M | Import won deals from the internal B2B lead pipeline as draft invoices (read-only link) | PROP | PROP | CONDITIONAL | R5 | SCR-122 |  | CON-33 | WP-31 | Full-stack | Given synthetic fixture FIX-M-116 for SCR-122, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-122), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-117 | F-D19 | D | Ad-spend in R1 profit: Amazon Ads, Google and Meta spend read for the compat Advertising line, blended ROAS/POAS and variable-expense bases | PROP | OBS | IN | R1 | SCR-011,SCR-120 | CALC-079,CALC-059,CALC-091 | CON-02,CON-08,CON-09 | WP-37 | Integration eng | Given synthetic fixture FIX-D-117 for SCR-011,SCR-120, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-083, GV-103, GV-131, GV-155 to the cent. | Spend only, for the Advertising line; other ad platforms by CSV import (ESTIMATE flag until reconciled)
REQ-118 | F-B18 | B | Period comparisons (Δ, Δ%, previous period, YoY) on tiles, P&L and trends | OBS | OBS | IN | R1 | SCR-010,SCR-013,SCR-015 | CALC-108 |  | WP-08 | Frontend | Given synthetic fixture FIX-B-118 for SCR-010,SCR-013,SCR-015, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-146 to the cent.
REQ-119 | F-K01 | K | Connector: Amazon SP-API (Orders, Finances, Reports, FBA Inventory, Inbound, Sales, Listings read) | DOC | S27,S28,S29,S30,S35 | IN | R0 | SCR-100 |  | CON-01 | WP-05 | Integration eng | Given synthetic fixture FIX-K-119 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | All Amazon marketplaces across NA, EU and FE regions (WP-38): Amazon.in on the EU endpoint in R0/R1; UK/FR/DE/US and every other marketplace in R2. Private developer registration; no restricted PII roles.
REQ-120 | F-K02 | K | Connector: Amazon Ads API — spend reporting only (SP/SB/SD v3: spend by campaign, advertised product, day) | DOC | S33,S34 | IN | R1 | SCR-100 |  | CON-02 | WP-37 | Integration eng | Given synthetic fixture FIX-K-120 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Read-only cost input for the Advertising line; no campaign analytics, no bid or budget writes (marketing omitted v0.3)
REQ-121 | F-K03 | K | Connector: Amazon Brand Analytics / Search Terms (via Reports API) | DOC | S05,S06,S29 | OMITTED | — | SCR-100 |  | CON-03 |  |  | Given synthetic fixture FIX-K-121 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-122 | F-K04 | K | Connector: Amazon Attribution | DOC | S12 | OMITTED | — | SCR-100 |  | CON-04 |  |  | Given synthetic fixture FIX-K-122 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-123 | F-K05 | K | Connector: Shopify Admin GraphQL (orders, products, inventory, customers L1/L2, fulfillments) | DOC | S20,S21,S22,S23,S24,S25,S26 | IN | R1 | SCR-100 |  | CON-05 | WP-12 | Integration eng | Given synthetic fixture FIX-K-123 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | read_all_orders approval for >60 days; bulk ops ≤5 concurrent; webhooks HMAC + reconciliation; protected data L1/L2
REQ-124 | F-K06 | K | Connector: Shopify Payments payouts & balance transactions | DOC | S20 | IN | R1 | SCR-100 |  | CON-06 | WP-12 | Integration eng | Given synthetic fixture FIX-K-124 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | read_shopify_payments_payouts; Payout.summary; BalanceTransaction.fee
REQ-125 | F-K07 | K | Connector: Other payment gateways (Razorpay/PayPal/Stripe) — fee import | PROP | PROP | CONDITIONAL | R2 | SCR-100 |  | CON-07 | WP-23 | Integration eng | Given synthetic fixture FIX-K-125 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Manual CSV fallback default; API per gateway TBD
REQ-126 | F-K08 | K | Connector: Google Ads — spend only | DOC | S01,S02 | IN | R1 | SCR-100 |  | CON-08 | WP-37 | Integration eng | Given synthetic fixture FIX-K-126 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Read-only daily spend for the Advertising line (marketing omitted v0.3)
REQ-127 | F-K09 | K | Connector: Meta (Facebook/Instagram) Ads — spend only | DOC | S01,S02 | IN | R1 | SCR-100 |  | CON-09 | WP-37 | Integration eng | Given synthetic fixture FIX-K-127 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Read-only daily spend for the Advertising line (marketing omitted v0.3)
REQ-128 | F-K10 | K | Connector: Microsoft/Bing Ads | DOC | S02 | OMITTED | — | SCR-100 |  | CON-10 |  |  | Given synthetic fixture FIX-K-128 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-129 | F-K11 | K | Connector: TikTok Ads — spend only (for TikTok Shop and Shopify profit) | DOC | S01 | CONDITIONAL | R2 | SCR-100 |  | CON-11 | WP-23 | Integration eng | Given synthetic fixture FIX-K-129 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Read/report scope only; daily spend for the Advertising line; CONDITIONAL on API access, else CSV import flagged ESTIMATE (review finding v0.3-12)
REQ-130 | F-K12 | K | Connector: Snapchat Ads | DOC | S01 | OMITTED | — | SCR-100 |  | CON-12 |  |  | Given synthetic fixture FIX-K-130 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-131 | F-K13 | K | Connector: Pinterest Ads | DOC | S01,S02 | OMITTED | — | SCR-100 |  | CON-13 |  |  | Given synthetic fixture FIX-K-131 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-132 | F-K14 | K | Connector: Taboola | DOC | S02 | OMITTED | — | SCR-100 |  | CON-14 |  |  | Given synthetic fixture FIX-K-132 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-133 | F-K15 | K | Connector: Klaviyo | DOC | S02 | OMITTED | — | SCR-100 |  | CON-15 |  |  | Given synthetic fixture FIX-K-133 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-134 | F-K16 | K | Connector: Walmart Marketplace / WFS / Walmart Connect & SEM spend (read) | DOC | S09,S11,S14 | IN | R2 | SCR-100 |  | CON-16 | WP-23 | Integration eng | Given synthetic fixture FIX-K-134 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | US/CA/MX; OAuth token 15 min; settlement reports; WFS & MCF flag; ad spend read only
REQ-135 | F-K17 | K | Connector: eBay | DOC | S11,S18 | IN | R2 | SCR-100 |  | CON-17 | WP-23 | Integration eng | Given synthetic fixture FIX-K-135 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Orders, fees, payouts, returns; order-level COGS/shipping import
REQ-136 | F-K18 | K | Connector: TikTok Shop | DOC | S02 | IN | R2 | SCR-100 |  | CON-18 | WP-23 | Integration eng | Given synthetic fixture FIX-K-136 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Commerce orders, fees, settlements; distinct from TikTok Ads (omitted)
REQ-137 | F-K19 | K | Connector: CJ Dropshipping | DOC | S02 | IN | R5 | SCR-100 |  | CON-19 | WP-39 | Integration eng | Given synthetic fixture FIX-K-137 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-138 | F-K20 | K | Connector: ShipStation (actual shipping cost) | DOC | S02,S49 | IN | R5 | SCR-100 |  | CON-20 | WP-39 | Integration eng | Given synthetic fixture FIX-K-138 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-139 | F-K21 | K | Connector: Flexport / SFN | DOC | S02 | IN | R5 | SCR-100 |  | CON-21 | WP-39 | Integration eng | Given synthetic fixture FIX-K-139 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-140 | F-K22 | K | Connector: Veeqo | DOC | S02,OBS | IN | R5 | SCR-100 |  | CON-22 | WP-39 | Integration eng | Given synthetic fixture FIX-K-140 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-141 | F-K23 | K | Connector: Private Google Sheets / CSV-XLSX URL feeds (COGS, landed cost, expenses) | DOC | S12,OBS | IN | R1 | SCR-100 |  | CON-23 | WP-09 | Full-stack | Given synthetic fixture FIX-K-141 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Daily sync; schema validation; untrusted content
REQ-142 | F-K24 | K | Connector: Amazon Solicitations API (review requests) | DOC | S31 | OMITTED | — | SCR-100 |  | CON-24 |  |  | Given synthetic fixture FIX-K-142 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-143 | F-K25 | K | Connector: Amazon Listings Items (price patch) — repricer writes | DOC | S32 | CONDITIONAL | R4 | SCR-100 |  | CON-25 | WP-22 | Full-stack | Given synthetic fixture FIX-K-143 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Simulation-first; maker-checker; kill switch
REQ-144 | F-K26 | K | Connector: Amazon Ads write (bids/budgets/negatives) | DOC | S04,S34 | OMITTED | — | SCR-100 |  | CON-26 |  |  | Given synthetic fixture FIX-K-144 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-145 | F-K27 | K | Connector: QuickBooks / Tally export (accounting) | DOC | OBS,S49 | IN | R5 | SCR-100 |  | CON-27 | WP-25 | Full-stack | Given synthetic fixture FIX-K-145 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | File export first; API later
REQ-146 | F-K28 | K | Connector: Anthropic API (optional explain layer) | DOC | S37 | CONDITIONAL | R5 | SCR-100 |  | CON-28 | WP-26 | Backend | Given synthetic fixture FIX-K-146 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Aggregates only; never authoritative numbers; ₹ cost metered
REQ-147 | F-K29 | K | Connector: Subscription provider (Shopify subscription app of record) | DOC | S20 | CONDITIONAL | R2 | SCR-100 |  | CON-29 | WP-23 | Integration eng | Given synthetic fixture FIX-K-147 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | read_own_subscription_contracts is app-scoped; true contracts only via app of record or its export; else repeat-order heuristic labelled as such
REQ-148 | F-K30 | K | Connector: Courier / 3PL fulfilment cost source (e.g., Eshopbox, courier invoices) — CSV/XLSX first, API discovery | OBS | OBS,PROP | CONDITIONAL | R1 | SCR-100 |  | CON-32 | WP-35 | Integration eng | Given synthetic fixture FIX-K-148 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Actual forward/return/RTO/COD charges per order replace shipping-profile estimates; API availability DISCOVERY
REQ-149 | F-K31 | K | Connector: Internal B2B lead pipeline app (won deals → draft B2B invoices), read-only | PROP | PROP | CONDITIONAL | R5 | SCR-100 |  | CON-33 | WP-31 | Full-stack | Given synthetic fixture FIX-K-149 for SCR-100, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-100), then all listed controls render, validation/errors behave as specified, and the action is audit-logged. | Owner-confirmed export/API; never auto-posts invoices
REQ-150 | F-L01 | L | Reports catalogue: dashboard by day/month/product, orders, sales by product/month, repeat, stock history, COGS, refunds (ads-performance report omitted v0.3) | OBS | OBS,S11 | IN | R1 | SCR-110 |  |  | WP-11 | Backend | Given synthetic fixture FIX-L-150 for SCR-110, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-110), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-151 | F-L02 | L | CSV/XLSX export, scheduled e-mail / private link destinations, permissions | OBS | OBS | IN | R1 | SCR-111 |  |  | WP-11 | Backend | Given synthetic fixture FIX-L-151 for SCR-111, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-111), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-152 | F-L03 | L | Claude-ready export bundles (schema + data dictionary) | PROP | PROP | IN | R1 | SCR-110 |  |  | WP-11 | Backend | Given synthetic fixture FIX-L-152 for SCR-110, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-110), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-153 | F-L04 | L | Cashflow (payout-based) & settlement bridge | OBS | OBS | IN | R5 | SCR-112,SCR-113 | CALC-027,CALC-073 | CON-01 | WP-25 | Full-stack | Given synthetic fixture FIX-L-153 for SCR-112,SCR-113, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-034, GV-098 to the cent.
REQ-154 | F-L05 | L | QuickBooks / accounting export | OBS | OBS | IN | R5 | SCR-113 |  | CON-27 | WP-25 | Full-stack | Given synthetic fixture FIX-L-154 for SCR-113, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-113), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-155 | F-L06 | L | Help, glossary, calculation tooltips & lineage | OBS+PROP | OBS | IN | R1 | SCR-116 |  |  | WP-08 | Frontend | Given synthetic fixture FIX-L-155 for SCR-116, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-116), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-156 | F-L07 | L | Diagnostics: sync status, freshness, errors, data lineage | PROP | PROP | IN | R0 | SCR-114 |  |  | WP-06 | Backend | Given synthetic fixture FIX-L-156 for SCR-114, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-114), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-157 | F-L08 | L | Responsive web + mobile PWA; push/offline where feasible | DOC | S03,S08 | CONDITIONAL | R5 | SCR-117 |  |  | WP-24 | Frontend | Given synthetic fixture FIX-L-157 for SCR-117, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-117), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-158 | F-L09 | L | Browser extension (product page profit calc) | DOC | S03 | CONDITIONAL | R5 | SCR-117 |  |  | WP-24 | Frontend | Given synthetic fixture FIX-L-158 for SCR-117, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-117), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-159 | F-L10 | L | Dark/light mode, accessibility (WCAG 2.1 AA), localization (EN; INR/GBP/EUR/USD formats) | OBS | OBS | IN | R1 | SCR-010 |  |  | WP-33 | Frontend | Given synthetic fixture FIX-L-159 for SCR-010, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-010), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-160 | F-L11 | L | Data export/delete (GDPR/DPDP), audit log | DOC | S24 | IN | R0 | SCR-101 |  |  | WP-03 | Backend lead | Given synthetic fixture FIX-L-160 for SCR-101, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-101), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-161 | F-L12 | L | Optional AI explain layer (aggregates only) / MCP-style read connector | OBS | OBS,S37 | CONDITIONAL | R5 | SCR-118 |  | CON-28 | WP-26 | Backend | Given synthetic fixture FIX-L-161 for SCR-118, when the user performs the screen-level acceptance test in 03_UI_UX_Atlas.md (SCR-118), then all listed controls render, validation/errors behave as specified, and the action is audit-logged.
REQ-162 | F-B01 | B | Profit tiles Today/Yesterday/MTD/Forecast/Last month with comparisons | OBS | OBS | IN | R1 | SCR-010,SCR-016 | CALC-002,CALC-013,CALC-045,CALC-108 | CON-01 | WP-08 | Frontend | Fixture GV-030: sales unchanged when attributed revenue present.
REQ-163 | F-J04 | J | Multichannel fulfillment order filtering & economic dedup (MCF/WFS) | OBS | OBS,S11 | IN | R2 | SCR-091,SCR-101 | CALC-047 |  | WP-13 | Financial/data eng | GV-031/032.
REQ-164 | F-D01 | D | Marketplace fee taxonomy incl. India-specific (TDS, affordability, technology, closing) & unknown codes | OBS | OBS,S03 | IN | R1 | SCR-032,SCR-011 | CALC-003,CALC-067,CALC-109 | CON-01 | WP-07 | Financial/data eng | GV-011.
REQ-165 | F-D03 | D | Actual vs estimated shipping; ShipStation actuals | DOC | S01,S49 | IN | R1 | SCR-033 | CALC-020 | CON-32 | WP-13 | Financial/data eng | GV-020/021. | R1 uses courier/3PL actuals (CON-32, WP-35); ShipStation actuals (CON-20) arrive with WP-39 in R5
REQ-166 | F-C03 | C | Landed-cost elements per batch | OBS | OBS | IN | R1 | SCR-022 | CALC-008 |  | WP-09 | Full-stack | GV-013.
REQ-167 | F-D02 | D | Refunds: partial, refund-without-return, unsellable, fee/tax reversals | OBS | OBS,S17 | IN | R1 | SCR-034 | CALC-004,CALC-009,CALC-053,CALC-054,CALC-082 |  | WP-07 | Financial/data eng | GV-016. | FBM refund reasons added by vendor 2026-09-10
REQ-168 | F-C01 | C | COGS policies: fixed, percentage, by period, batch, FIFO, weighted average | OBS | OBS,S01,S13 | IN | R1 | SCR-021 | CALC-005,CALC-006,CALC-007,CALC-078 |  | WP-09 | Full-stack | GV-008.
REQ-169 | F-C08 | C | Missing/zero COGS detection and alert | DOC | S18 | IN | R1 | SCR-076 | CALC-043 |  | WP-34 | Financial/data eng | GV-018.
REQ-170 | F-B04 | B | P&L table by day/month with heatmap and compare/YoY | OBS | OBS,S13,S18 | IN | R1 | SCR-013 | CALC-013,CALC-050,CALC-051,CALC-108 |  | WP-08 | Frontend | GV-017/019.
REQ-171 | F-F02 | F | Cohorts, retention, repeat rate, time-to-second purchase, CAC, payback with maturity flags | PROP | S01,PROP | IN | R2 | SCR-051 | CALC-034,CALC-035,CALC-036 |  | WP-14 | Data eng | GV-035/036.
REQ-172 | F-F04 | F | Subscription contracts vs repeat orders (SnS count observed) | OBS | OBS,S20 | CONDITIONAL | R2 | SCR-051 |  | CON-29 | WP-14 | Data eng | GV-037. | No cross-app contract read on Shopify
REQ-173 | F-I02 | I | Guardrails: marketplace bounds, ±% caps, stale-data stop, kill switch, simulation, approval | DOC | S10,PROP | CONDITIONAL | R4 | SCR-080,SCR-047 | CALC-041,CALC-075 |  | WP-20 | Backend | GV-040/041. | vendor added Was-price cap and private-label velocity mode 2026-09-28
REQ-174 | F-D09 | D | Fee amortization (daily) for storage/inbound/removal etc. | OBS | OBS,S15 | IN | R1 | SCR-101 | CALC-024 |  | WP-07 | Financial/data eng | GV-025.
REQ-175 | F-L07 | L | Diagnostics: sync status, freshness, errors, data lineage | PROP | PROP | IN | R0 | SCR-114 |  |  | WP-06 | Backend | GV-046.
REQ-176 | F-I02 | I | Guardrails: marketplace bounds, ±% caps, stale-data stop, kill switch, simulation, approval | DOC | S10,PROP | CONDITIONAL | R4 | SCR-080,SCR-047 | CALC-041,CALC-075 |  | WP-20 | Backend | Contract tests WP-20. | vendor added Was-price cap and private-label velocity mode 2026-09-28
REQ-177 | F-L12 | L | Optional AI explain layer (aggregates only) / MCP-style read connector | OBS | OBS,S37 | CONDITIONAL | R5 | SCR-118 |  | CON-28 | WP-26 | Backend | Prompt-injection + authority tests.
REQ-178 | F-B13 | B | Sellerboard-compatible P&L mode (same line names, order and definitions) with contribution-margin toggle | OBS-R | OBS | IN | R1 | SCR-011,SCR-013 | CALC-050,CALC-051,CALC-052 |  | WP-34 | Financial/data eng | GV-073/074. | Formulas reconciled against authorized session
REQ-179 | F-E12 | E | Dual attribution: platform-reported vs first/last-visit attributed, customer journey | OBS-R | OBS | OMITTED | R2 | SCR-133,SCR-134 | CALC-061,CALC-056 | CON-05,CON-08,CON-09 |  |  | GV-030, GV-093. | OMITTED v0.3 — marketing function removed by Owner 2026-10-10; not to be built
REQ-180 | F-M02 | M | Manual B2B invoice entry with product master lines, HSN, auto GST split, freight, warehouse/batch; draft → approved → posted (maker-checker) | PROP | R-B2B | IN | R1 | SCR-123 | CALC-093,CALC-094,CALC-095,CALC-096 |  | WP-31 | Full-stack | GV-105..107.
REQ-181 | F-M07 | M | B2B in unified dashboard by customer/territory/salesperson with contribution and intercompany elimination | PROP | R-B2B | IN | R1 | SCR-120,SCR-121,SCR-127 | CALC-097,CALC-100,CALC-101,CALC-110 |  | WP-32 | Financial/data eng | GV-114.
REQ-182 | F-M04 | M | B2B bulk import (CSV/XLSX) with validation and duplicate detection; accounting export | PROP | R-B2B | IN | R1 | SCR-126 | CALC-100 |  | WP-31 | Full-stack | GV-113. | R1 accounting export is a file (CSV/XLSX); the accounting API connector CON-27 is R5
REQ-183 | F-D16 | D | Actual courier/3PL fulfilment cost import replacing profile estimates | PROP | OBS | CONDITIONAL | R1 | SCR-033,SCR-136 | CALC-105 | CON-32 | WP-35 | Integration eng | GV-117. | Observed: Shopify shipping profile mirrors customer-charged amount; pick&pack zero
REQ-184 | F-D12 | D | Shopify revenue composition: gross sales, discounts, shipping charged, refunds, tips, chargebacks, gift cards | OBS-R | OBS | IN | R1 | SCR-011,SCR-120 | CALC-076,CALC-052 | CON-05 | WP-13 | Financial/data eng | GV-090.
REQ-185 | F-A11 | A | All Amazon marketplaces (NA, EU, FE regions — e.g. US, CA, MX, BR, UK, IE, DE, FR, IT, ES, NL, BE, PL, SE, TR, AE, SA, EG, IN, JP, AU, SG, ZA): marketplace master with currency, timezone, tax regime and fee codes; 'All marketplaces' selector | DOC | S04,OBS | IN | R2 | SCR-101,SCR-010 | CALC-113,CALC-026 | CON-01 | WP-38 | Integration eng | Given synthetic fixture FIX-MKT-001 for SCR-101,SCR-010, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-033, GV-152, GV-153 to the cent. | Sellerboard's PPC page lists 23 Amazon marketplaces (S04) — used as the marketplace list; India in R0/R1, all others in R2
REQ-186 | F-J06 | J | Walmart / eBay / TikTok Shop fee, settlement and refund mapping into the Sellerboard-compatible P&L lines (unknown fee types → Unclassified + alert) | PROP | S09,S11,S18,PROP | IN | R2 | SCR-090,SCR-032 | CALC-114,CALC-067 | CON-16,CON-17,CON-18 | WP-23 | Integration eng | Given synthetic fixture FIX-J-186 for SCR-090,SCR-032, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-091, GV-154 to the cent. | Mapping is a PROPOSED transparent rule; parity checked line by line in the parallel run where Sellerboard data exists
REQ-187 | F-J07 | J | Walmart Connect / SEM ad spend as the Walmart Advertising line (spend only) | DOC | S14 | IN | R2 | SCR-090 | CALC-079 | CON-16 | WP-23 | Integration eng | Given synthetic fixture FIX-J-187 for SCR-090, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-103, GV-155 to the cent. | Spend only; no Walmart campaign analytics (marketing omitted)
REQ-188 | F-D19 | D | Ad-spend in R1 profit: Amazon Ads, Google and Meta spend read for the compat Advertising line, blended ROAS/POAS and variable-expense bases | PROP | OBS | IN | R1 | SCR-011,SCR-120 | CALC-079,CALC-059,CALC-091 | CON-02,CON-08,CON-09 | WP-37 | Integration eng | Connector scope review: CON-02/08/09/16 tokens hold read/report scopes only; no route or menu item exists for omitted screens. | Spend only, for the Advertising line; other ad platforms by CSV import (ESTIMATE flag until reconciled)
REQ-189 | F-A11 | A | All Amazon marketplaces (NA, EU, FE regions — e.g. US, CA, MX, BR, UK, IE, DE, FR, IT, ES, NL, BE, PL, SE, TR, AE, SA, EG, IN, JP, AU, SG, ZA): marketplace master with currency, timezone, tax regime and fee codes; 'All marketplaces' selector | DOC | S04,OBS | IN | R2 | SCR-101,SCR-010 | CALC-113,CALC-026 | CON-01 | WP-38 | Integration eng | GV-152/153 pass; adding a synthetic marketplace row enables ingestion without a code change. | Sellerboard's PPC page lists 23 Amazon marketplaces (S04) — used as the marketplace list; India in R0/R1, all others in R2
REQ-190 | F-G11 | G | Walmart WFS inventory and inbound shipments in the inventory planner (Walmart Inventory Planner parity), alongside FBA | DOC | S11,S09 | IN | R3 | SCR-060,SCR-063 | CALC-037,CALC-038,CALC-039,CALC-040 | CON-16 | WP-15 | Full-stack | Given synthetic fixture FIX-G-190 for SCR-060,SCR-063, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-038, GV-039, GV-052, GV-063, GV-133, GV-134 to the cent. | Sellerboard.com added a Walmart Inventory Planner (2026-02-26); WFS data arrives with WP-23 in R2, planner views in R3
REQ-191 | F-A12 | A | Amazon cross-border fulfilment: Pan-EU / EFN and Remote Fulfillment fee codes, pooled FBA stock across marketplaces, stock-transfer flags for VAT | PROP | PROP | IN | R2 | SCR-101,SCR-060 | CALC-067,CALC-092,CALC-113 | CON-01 | WP-38 | Integration eng | Given synthetic fixture FIX-A-191 for SCR-101,SCR-060, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-091, GV-132, GV-152, GV-153 to the cent. | Fee codes and VAT on stock transfers need CA confirmation per country (A-22); pooled stock never double counted
REQ-192 | F-J08 | J | Walmart and eBay report pages (orders, products, daily, monthly) in the reports catalogue | DOC | S11 | IN | R2 | SCR-110 |  | CON-16,CON-17 | WP-23 | Integration eng | Given synthetic fixture FIX-J-192 for SCR-110, when the user opens the screen, then all listed columns/controls render and values match golden vectors to the cent. | Same report layouts as Amazon/Shopify; channel filter
REQ-193 | F-J09 | J | Single source for Walmart Connect / SEM spend per ad account (connector or settlement, never both) | PROP | PROP | IN | R2 | SCR-090,SCR-100 | CALC-079,CALC-114 | CON-16 | WP-23 | Integration eng | Given synthetic fixture FIX-J-193 for SCR-090,SCR-100, when the user opens the screen, then all listed columns/controls render and values match golden vectors GV-103, GV-154, GV-155 to the cent. | Review finding v0.3-8

## Formula_Coverage_v02
audit_id | app | area | metric_or_rule | sellerboard_definition | evidence | sources | sow_calc_before | status_before | v02_action | sow_calc_after | v03_scope
FA-001 | COM | P&L | Sales | Order item revenue, VAT/GST-inclusive in IN/UK/EU marketplaces | OBS | OBS,S03 | CALC-001 | COVERED | Add compat label 'Sales' (tax-inclusive) to CALC-001 | CALC-001 | IN
FA-002 | COM | P&L | Promo | Promotional rebates, negative | OBS | OBS | CALC-002 | PARTIAL | Separate P&L line in compat stack | CALC-050 | IN
FA-003 | COM | P&L | Advertising cost (SP+SB+SBV+SD+RAS+external+flagged expenses, optional local VAT) | Amazon Ads + connected external spend + expenses flagged as advertising; setting adds local GST/VAT | DOC | S12,OBS,help | CALC-012 | PARTIAL | New composition contract | CALC-079 | IN
FA-004 | COM | P&L | Shipping costs (FBM profiles) | Profiles none / = customer charged / price / units / weight; tiers, zones, date ranges; precedence; per-order import overrides | DOC | help,OBS | CALC-020 | PARTIAL | Extend CALC-020 rules + precedence | CALC-020 | IN
FA-005 | COM | P&L | Giftwrap | Giftwrap line; display toggle only | OBS | OBS,help | — | MISSING | Add line in compat stack | CALC-050 | IN
FA-006 | COM | P&L | Refund cost | Refunded amount + non-refunded fees + refund commission + lost COGS of unsellable returns; recovery % | DOC | S03,help | CALC-004,CALC-009 | PARTIAL | Extend CALC-004/009 with recovery % | CALC-004 | IN
FA-007 | COM | P&L | Amazon fees (100+ types incl. India TDS, affordability, technology) | Imported fee events; account-level allocation not documented | OBS | OBS,S03 | CALC-003 | PARTIAL | Allocation contract for account-level fees | CALC-067 | IN
FA-008 | COM | P&L | Cost of goods (sellable returns restore COGS) | COGS of units sold; restored for sellable returns | DOC | help | CALC-005..007 | COVERED | — | CALC-005 | IN
FA-009 | COM | P&L | VAT / GST line (MF-VAT split documented only, S18) | Output tax removed as a line (reconciled); MF-VAT separate per documentation | OBS-R | OBS,S18 | CALC-002,CALC-025 | PARTIAL | Explicit output-tax line contract | CALC-052 | IN
FA-010 | COM | P&L | Gross profit | Sales + Promo + Advertising + Shipping + Giftwrap + Refund cost + Amazon fees + COGS + VAT (signed) | OBS-R | OBS,help | CALC-010 | DIVERGENT | SOW gross profit excluded ads; add compat stack | CALC-050 | IN
FA-011 | COM | P&L | Indirect expenses | One-time/weekly/monthly/daily; marketplace(s); products; ad flag; amortize | DOC | help,S16 | CALC-024 | COVERED | — | CALC-024 | IN
FA-012 | COM | P&L | Net profit | Gross profit + Indirect expenses (signed) | OBS-R | OBS,help | CALC-013 | DIVERGENT | Compat net profit + reconciliation to CM view | CALC-051 | IN
FA-013 | COM | P&L | Estimated payout | Projected disbursement; formula not documented | DOC | help | CALC-048 | COVERED | Label PROPOSED | CALC-048 | IN
FA-014 | COM | KPI | TACOS | Advertising ÷ Sales (tax-inclusive) | OBS-R | OBS,help | CALC-030 | COVERED | Basis = compat Sales | CALC-030 | IN
FA-015 | COM | KPI | Real ACOS | Ad spend ÷ total sales; product scope on Trends | DOC-F | help,S12 | CALC-031 | COVERED | — | CALC-031 | IN
FA-016 | COM | KPI | % Refunds | Refunded units ÷ units sold | OBS-R | OBS | CALC-019 | DIVERGENT | SOW used shipped units in window; compat contract | CALC-053 | IN
FA-017 | COM | KPI | Sellable returns % | Sellable returned units ÷ returned units | DOC | help | — | MISSING | New | CALC-054 | IN
FA-018 | COM | KPI | Margin | NP ÷ Sales, or ÷ (Sales − VAT) when 'use net sales' ON | OBS-R | OBS,help | CALC-014 | PARTIAL | Setting-driven denominator | CALC-014 | IN
FA-019 | COM | KPI | ROI | Net profit ÷ ¦COGS¦ | OBS-R | OBS | CALC-015 | COVERED | — | CALC-015 | IN
FA-020 | COM | KPI | Active subscriptions (SnS) & revenue penetration | Count; SnS sales ÷ sales | DOC | help | — | MISSING | New | CALC-072 | IN
FA-021 | COM | KPI | Sessions, Unit session % | Units ÷ sessions | OBS-R | OBS | CALC-018 | COVERED | — | CALC-018 | IN
FA-022 | COM | KPI | BSR | Rank snapshot with trend arrow | OBS | OBS | — | MISSING | Display field + delta | CALC-085 | IN
FA-023 | COM | KPI | Average selling price | Revenue ÷ units | OBS | S14,OBS | CALC-016 | COVERED | — | CALC-016 | IN
FA-024 | BOTH | KPI | This month (forecast) | Method not documented | NF | OBS | CALC-045 | COVERED | Label PROPOSED run-rate + seasonality option | CALC-045 | IN
FA-025 | COM | Products | Profit per unit | Price − COGS − FBA fee − referral fee − VAT | DOC | help | — | MISSING | New | CALC-066 | IN
FA-026 | COM | Products | Value of unsellable returns % | % of COGS recovered on unsellable returns | DOC | help | CALC-009 | PARTIAL | Recovery % input | CALC-009 | IN
FA-027 | COM | Costing | COGS by period / weighted / FIFO; per marketplace; cost elements | As documented | OBS | OBS,help | CALC-005..008 | COVERED | — | CALC-005 | IN
FA-028 | COM | Costing | FIFO oversold: last batch / zero / fixed | Setting | OBS | OBS,S13 | CALC-007 | COVERED | — | CALC-007 | IN
FA-029 | COM | Costing | Closing a PO creates a cost batch; transport allocated | PO close → batch | DOC | blog 2026-10-02 | CALC-008 | PARTIAL | PO-close batch + freight allocation | CALC-086 | IN
FA-030 | COM | Costing | Grade & Resell COGS exclusion | Original COGS excluded | DOC | help | — | MISSING | New guard | CALC-080 | IN
FA-031 | COM | Costing | COGS import by product/batch/order/SKU/EAN/UPC; daily Sheets/URL | Import keys | DOC | blog 2026-10-08,S12 | CON-23 | PARTIAL | Identifier matching rule | CALC-087 | IN
FA-032 | COM | Fees | Amortize Amazon fees daily (19 types) | Spread over period | OBS | OBS,S15 | CALC-024 | COVERED | — | CALC-024 | IN
FA-033 | COM | Fees | Ignore FBA inbound shipment costs (else allocated by volume & weight) | Inbound allocation | DOC | help,OBS | — | MISSING | New allocation | CALC-067 | IN
FA-034 | COM | Fees | Amazon fees include GST recoverable (+ start date); TCS recoverable | Reduce fee cost by recoverable tax | OBS | OBS | CALC-025 | COVERED | — | CALC-025 | IN
FA-035 | COM | Fees | Add local GST to advertising costs | Non-recoverable tax on ad spend | OBS | OBS | — | MISSING | Part of ad composition | CALC-079 | IN
FA-036 | COM | Refunds | Ignore deferred refunds until released | Book on release date | OBS | OBS | CALC-004 | PARTIAL | Booking-date option | CALC-082 | IN
FA-037 | COM | Refunds | Assume pending returns unsellable | No COGS restore until received | OBS | OBS | CALC-009 | PARTIAL | Option | CALC-009 | IN
FA-038 | COM | Refunds | Consider returned condition despite restocking fee | Condition overrides heuristic | OBS | OBS | CALC-009 | PARTIAL | Option | CALC-009 | IN
FA-039 | COM | MCF | Ignore multi-channel orders (exclude MCF fees and COGS) | Exclude from Amazon account | DOC | help,OBS,S11 | CALC-047 | PARTIAL | Assign MCF fee+COGS to Shopify channel | CALC-047 | IN
FA-040 | COM | FX | Currency switch uses rate of LAST day of period | Presentation FX | DOC | help | CALC-026 | DIVERGENT | Compat presentation mode | CALC-081 | IN
FA-041 | COM | PPC | ACOS | Ad spend ÷ PPC sales | OBS-R | OBS,help | CALC-029 | COVERED | — | CALC-029 | OMITTED (marketing, v0.3)
FA-042 | COM | PPC | ROAS | PPC sales ÷ ad spend | OBS | OBS | CALC-028 | COVERED | — | CALC-028 | OMITTED (marketing, v0.3)
FA-043 | COM | PPC | PPC profit (incl. VAT; previous-month per-order estimates) | Signed sum incl. VAT | OBS-R | OBS,help,blog 09-18 | — | MISSING | New | CALC-055 | OMITTED (marketing, v0.3)
FA-044 | COM | PPC | Break-even ACOS | (Profit + ad spend) ÷ PPC sales | OBS-R | OBS,help | CALC-049 | PARTIAL | Replace proposed contract with documented formula | CALC-049 | OMITTED (marketing, v0.3)
FA-045 | COM | PPC | Break-even bid | BE-ACOS ÷ ACOS × CPC | DOC-F | help | — | MISSING | New | CALC-057 | OMITTED (marketing, v0.3)
FA-046 | COM | PPC | CPC, CTR, cost per order, conversion, budget utilisation | Standard ratios | DOC-F | help,OBS | — | MISSING | New | CALC-056 | OMITTED (marketing, v0.3)
FA-047 | COM | PPC | Bid recommendation strategies; target ACOS/margin | Proprietary | DOC | S04 | — | PARTIAL | PROPOSED transparent rule; no parity claim | CALC-088 | OMITTED (marketing, v0.3)
FA-048 | COM | PPC | Day parting | base × multiplier ≤ max; nightly 28-day rebuild | DOC-F | blog 2026-10-08,OBS | — | MISSING | New (write — conditional) | CALC-058 | OMITTED (marketing, v0.3)
FA-049 | COM | PPC | Search-term share | My ÷ Total | DOC | help | — | MISSING | New | CALC-074 | OMITTED (marketing, v0.3)
FA-050 | COM | Attribution | Amazon Attribution profit & ROAS (14-day) | Sales − spend − COGS − fees − VAT | DOC-F | blog 2026-09-10 | CALC-032 | PARTIAL | New contract | CALC-060 | OMITTED (marketing, v0.3)
FA-051 | COM | Inventory | Sales velocity (weighted windows, OOS excluded) | Σ weight × units/in-stock days (reconciled on .io, see FA-095) | DOC | OBS,help | CALC-037 | DIVERGENT | Replace simple average | CALC-037 | IN
FA-052 | COM | Inventory | Days of stock left | (on-hand + reserved) ÷ velocity | OBS-R | OBS | CALC-038 | PARTIAL | Define stock basis | CALC-038 | IN
FA-053 | BOTH | Inventory | Days until next order | Days of stock − (mfg + shipping + buffer) | OBS-R | OBS | — | MISSING | New | CALC-062 | IN
FA-054 | BOTH | Inventory | Recommended reorder quantity | velocity × season × (lead + target) − pipeline stock | OBS | OBS,help | CALC-039 | PARTIAL | Extend inputs; exact vendor formula NF | CALC-039 | IN
FA-055 | BOTH | Inventory | Stock value / potential sales / potential profit | units × COGS / price / profit-per-unit | OBS-R | OBS | — | MISSING | New | CALC-063 | IN
FA-056 | COM | Inventory | Funds needed, sales/profit at risk | Basis not documented | NF | OBS | — | MISSING | PROPOSED | CALC-064 | IN
FA-057 | BOTH | Inventory | Missed profit (est.) | OOS days × velocity × avg profit/unit | DOC | help,OBS | — | MISSING | New | CALC-065 | IN
FA-058 | IO | Inventory | Profit forecast (30 days) | velocity × 30 × profit/unit | OBS | OBS | — | MISSING | New (PROPOSED stock cap) | CALC-089 | IN
FA-059 | COM | Inventory | Prep-center stock auto-reduction | Setting | OBS | OBS | CALC-040 | COVERED | — | CALC-040 | IN
FA-060 | COM | MoneyBack | Lost & damaged estimate (60 d) | Basis NF | DOC | help | CALC-044 | PARTIAL | Candidate contract | CALC-071 | IN
FA-061 | COM | MoneyBack | Refund without return (105 d) | Refund, no return, no reimbursement | DOC | help | CALC-044 | PARTIAL | Candidate contract | CALC-070 | IN
FA-062 | COM | MoneyBack | Reimbursement gap | COGS − reimbursement when lower | DOC-F | help | — | MISSING | New | CALC-068 | IN
FA-063 | COM | MoneyBack | FBA fee change overcharge | (new − old) × units | DOC | help | — | MISSING | New | CALC-069 | IN
FA-064 | COM | LTV | Acc. sales/units/orders per buyer (3–48 m) | Trailing windows; buyer identity NF | OBS | OBS,help | CALC-033 | DIVERGENT | Trailing-window compat metric; keep cohort LTV | CALC-084 | IN
FA-065 | COM | Customers | Repeat customer (same brand) | Buyer with >1 order same brand | DOC | help | CALC-035 | PARTIAL | Brand-scoped rule | CALC-083 | IN
FA-066 | COM | Cashflow | Cash on hand running total; 3-period forecast | Payouts, investments, expenses, goods, dividends | DOC | help,OBS | — | MISSING | New | CALC-073 | IN
FA-067 | COM | Repricer | Min/max; floor; guardrails CPT, +25% median, ±50% initial, +50% Was price | As documented | DOC | S10,blog 09-28 | CALC-041 | PARTIAL | Guardrail envelope | CALC-075 | IN
FA-068 | COM | Alerts | Alert types, priority, routing, dedup | As observed | OBS | OBS | CALC-043 | COVERED | — | CALC-043 | IN
FA-069 | COM | Reviews | Request-a-review eligibility | 5–30 days after delivery, once | DOC | S31 | CALC-042 | COVERED | — | CALC-042 | OMITTED (marketing, v0.3)
FA-070 | IO | P&L | Sales = Gross sales + Promo + Shipping charged + Refunded amount | Tax-inclusive | OBS-R | OBS | CALC-001,CALC-002 | DIVERGENT | Shopify revenue composition | CALC-076 | IN
FA-071 | IO | P&L | Chargeback, Tip lines | As observed | OBS | OBS | — | MISSING | Tips excluded; chargebacks cost | CALC-076 | IN
FA-072 | IO | P&L | Order status split; excluded statuses | As observed | OBS | OBS | — | MISSING | Order inclusion rule | CALC-090 | IN
FA-073 | IO | P&L | Units net vs returned quantity | As observed | OBS-R | OBS | CALC-019 | PARTIAL | Used in % refunds | CALC-053 | IN
FA-074 | IO | P&L | Shipping profiles incl. methods, domestic/international, returns shipping | As observed | OBS | OBS | CALC-020 | PARTIAL | Return shipping + method mapping | CALC-077 | IN
FA-075 | IO | P&L | Pick & pack incl. return processing | As observed | OBS | OBS | CALC-021 | PARTIAL | Return processing cost | CALC-077 | IN
FA-076 | IO | P&L | Payment fees = (Shopify % + gateway %) × amount + fixed; Auto = actual | As observed | OBS | OBS | CALC-022 | PARTIAL | Platform fee component & gateway table | CALC-022 | IN
FA-077 | IO | P&L | COGS = COGS sold − value of returned (restocked) | As observed | OBS-R | OBS | CALC-009 | COVERED | Map refund-COGS setting | CALC-009 | IN
FA-078 | IO | P&L | Tax = IGST + CGST (+SGST) − refunded tax | SGST absent → anomaly | OBS-R | OBS | CALC-025 | PARTIAL | Tax line with CGST=SGST check | CALC-052 | IN
FA-079 | IO | P&L | Gross profit = Sales + Ads + Shipping + Payment fees + COGS + Tax | Signed sum | OBS-R | OBS | CALC-010 | DIVERGENT | Compat stack (Shopify variant) | CALC-050 | IN
FA-080 | IO | P&L | Net profit = GP + Expenses | Signed sum | OBS-R | OBS | CALC-013 | DIVERGENT | Compat net profit | CALC-051 | IN
FA-081 | IO | KPI | AOV = Sales ÷ Orders | Tax-inclusive | OBS-R | OBS | CALC-017 | PARTIAL | Basis = compat Sales | CALC-017 | IN
FA-082 | IO | KPI | Blended ROAS = Sales ÷ Ad cost; POAS = Net profit ÷ Ad cost | As observed | OBS-R | OBS | — | MISSING | New | CALC-059 | IN
FA-083 | IO | KPI | CAC = Ad cost ÷ new customers | As observed | OBS | OBS | CALC-034 | COVERED | Define new-customer rule | CALC-034 | IN
FA-084 | IO | KPI | GP margin and NP margin on Sales | Tax-inclusive basis | OBS-R | OBS | CALC-014 | PARTIAL | GP margin + basis setting | CALC-014 | IN
FA-085 | IO | Marketing | Platform-reported vs attributed (first/last visit); NCR; CPO; conversion | Conversion reconciled; NCR/CPO observed only | OBS-R | OBS | CALC-032 | PARTIAL | Dual-view; never summed | CALC-061 | OMITTED (marketing, v0.3)
FA-086 | IO | Marketing | CPM, CTR, CPC, clicks, impressions | Standard | OBS | OBS | — | MISSING | Ad unit metrics | CALC-056 | OMITTED (marketing, v0.3)
FA-087 | IO | Marketing | Customer journey | As observed | OBS | OBS | CALC-032 | PARTIAL | Journey data contract | CALC-061 | OMITTED (marketing, v0.3)
FA-088 | IO | LTV | Acc. sales/units/orders/profit per buyer; customers; new; repurchase; CAC; days between orders; ROAS; POAS | Trailing windows | OBS | OBS | CALC-033..036 | DIVERGENT | Trailing-window set + cohort view | CALC-084 | IN
FA-089 | IO | Products | COGS types incl. % of price basis, From sellerboard.com, Tiered | As observed | OBS | OBS | CALC-005 | PARTIAL | Tiered + %-basis + shared COGS master | CALC-078 | IN
FA-090 | IO | Products | Country surcharge | Per-country table | OBS | OBS | CALC-020 | PARTIAL | Surcharge | CALC-077 | IN
FA-091 | IO | Expenses | Variable expense bases incl. % of Facebook/Google spend; ad flag | As observed | OBS | OBS | CALC-011 | PARTIAL | Enumerate bases | CALC-091 | IN
FA-092 | IO | Settings | Refunds displayed by order date vs refund date | Setting | OBS | OBS | CALC-004 | PARTIAL | Booking-date option | CALC-082 | IN
FA-093 | IO | Settings | Exclude orders by status / channel / tag | Setting | OBS | OBS | — | MISSING | Order inclusion rule | CALC-090 | IN
FA-094 | IO | Settings | Multi-product shipping sum vs highest | Setting | OBS | OBS | CALC-020 | COVERED | — | CALC-020 | IN
FA-095 | IO | Inventory | Weighted velocity, seasonality, lead-time components | As observed | OBS-R | OBS | CALC-037,CALC-039 | DIVERGENT | Replace/extend | CALC-037 | IN
FA-096 | IO | Inventory | Shopify locations incl. 3PL warehouses and factory | Location filter | OBS | OBS | CALC-040 | PARTIAL | Location→warehouse mapping | CALC-092 | IN
FA-097 | BOTH | Linking | Shared COGS ('From sellerboard.com'); Amazon product link | As observed | OBS | OBS | — | MISSING | Single product master | CALC-087 | IN
FA-098 | IO | Dashboard | Sales-channel filter; group by Parent/Brand/Channel/Bundle | As observed | OBS | OBS | — | PARTIAL | Channel dimension + bundle grouping | CALC-101 | IN
FA-099 | BOTH | Dashboard | Summary dashboard across accounts | Sum of accounts | OBS | OBS,S41 | — | PARTIAL | Unified multi-entity consolidation | CALC-101 | IN
FA-100 | COM | Fees | India Item TDS (s.194-O) presentation | Shown inside Amazon fees | OBS | OBS | CALC-025 | DIVERGENT | Presentation setting applied to both views | CALC-025 | IN
FA-101 | COM | P&L | Amazon shipping/giftwrap charges and chargebacks | Display toggle; mapping not documented | OBS | OBS | — | MISSING | PROPOSED mapping | CALC-109 | IN
FA-102 | BOTH | Dashboard | Period comparison (+% vs prior, Compare previous/YoY, trend Δ%) | As observed | OBS | OBS | — | MISSING | New contract | CALC-108 | IN
FA-103 | IO | P&L | Returns split (fully / partially refunded / unfulfilled) | As observed | OBS | OBS | — | MISSING | Return status rule | CALC-090 | IN
FA-104 | IO | Inventory | Inventory ROI and Margin columns | As observed | OBS | OBS | — | MISSING | Derived from stock value/potential | CALC-063 | IN
FA-105 | COM | KPI | Active SnS subscriptions count | As observed | OBS | OBS | — | MISSING | Count in SnS contract | CALC-072 | IN
FA-106 | BOTH | Inventory | Days-of-stock / next-order badge thresholds (red/yellow) | Observed badges; thresholds NF | OBS | OBS | — | MISSING | PROPOSED thresholds | CALC-062 | IN
FA-107 | COM | Settings | Ignore inactive listings; show reorder alerts | Settings | OBS | OBS | — | MISSING | Inclusion/alert rules | CALC-090 | IN
FA-108 | IO | Products | Attributed ads (manual ad→product assignment) | As observed | OBS | OBS | CALC-012 | PARTIAL | Ad allocation rule | CALC-079 | IN
FA-109 | COM | Inventory | Reorder growth %, AWD stock, private-label velocity mode, split POs | Documented inputs | DOC | help,blog | CALC-039 | PARTIAL | Extend reorder inputs | CALC-039 | IN
FA-110 | COM | Refunds | Refund reasons (FBA + FBM) | Documented | DOC | blog 2026-09-10 | — | MISSING | Reason dimension on refunds | CALC-053 | IN
FA-111 | COM | Alerts | Low-inventory-level fee risk (weekly, FNSKU) | Documented | DOC | blog 2026-09-23 | — | MISSING | PROPOSED risk rule | CALC-043 | IN
FA-112 | BOTH | Dashboard | Map view region metrics | As observed | OBS | OBS | — | MISSING | Region attribution | CALC-111 | IN
FA-113 | COM | PPC | Search-term harvest/negate, budget adjustments, keyword isolation | Proprietary | OBS | OBS,S04 | — | MISSING | PROPOSED rules, no parity | CALC-112 | OMITTED (marketing, v0.3)
FA-114 | IO | Marketing | Attributed ROAS, CPO, conversion, AOV | Conversion reconciled | OBS | OBS | CALC-032 | PARTIAL | Extend dual-attribution contract | CALC-061 | OMITTED (marketing, v0.3)
FA-115 | COM | PPC | Day parting time blocks (4×/day, block × weekday) | As observed | OBS | OBS | — | PARTIAL | Granularity setting | CALC-058 | OMITTED (marketing, v0.3)
FA-116 | COM | Marketplaces | Amazon marketplaces across NA/EU/FE (23 listed) incl. tax regime per marketplace (VAT, GST, marketplace-facilitator tax) | Marketplace list documented; per-marketplace tax display NF | DOC | S04,S18 | CALC-025 | PARTIAL | v0.3: marketplace master + regime rule (PROPOSED) | CALC-113 | IN
FA-117 | COM | Other channels | Walmart / eBay P&L lines (fees, WFS, Walmart Connect/SEM spend, returns) and TikTok Shop (.io) | Documented views; line mapping NF | DOC | S09,S11,S14,S18,S02 | — | MISSING | v0.3: channel fee mapping table (PROPOSED) | CALC-114 | IN
FA-B01 | NEW | B2B | B2B taxable value (line + invoice discounts) | Not in Sellerboard | PROP | R-B2B | — | MISSING | New | CALC-093 | IN
FA-B02 | NEW | B2B | GST split by place of supply (CGST+SGST / IGST / export LUT) | Rule 46 / IGST Act | PROP | R-B2B | — | MISSING | New | CALC-094 | IN
FA-B03 | NEW | B2B | B2B net sales, credit notes, freight charged | Ex-GST | PROP | R-B2B | — | MISSING | New | CALC-095 | IN
FA-B04 | NEW | B2B | B2B COGS by warehouse batch; FOC/samples to expense | Shared costing | PROP | R-B2B | — | MISSING | New | CALC-096 | IN
FA-B05 | NEW | B2B | B2B contribution | — | PROP | R-B2B | — | MISSING | New | CALC-097 | IN
FA-B06 | NEW | B2B | Receivables, TDS withheld, aging, MSME 45-day flag, DSO | — | PROP | R-B2B | — | MISSING | New | CALC-098 | IN
FA-B07 | NEW | B2B | Export invoice FX & realisation | FEMA | PROP | R-B2B | — | MISSING | New | CALC-099 | IN
FA-B08 | NEW | B2B | Dedup vs Shopify draft orders / Amazon Business; intercompany elimination | — | PROP | R-B2B | — | MISSING | New | CALC-100 | IN
FA-B11 | NEW | B2B | Intercompany COGS / unrealised profit elimination | — | PROP | R-B2B | — | MISSING | New | CALC-110 | IN
FA-B09 | NEW | B2B | Compliance flags: IRN 30-day, e-way bill, HSN rate master | — | PROP | R-B2B | — | MISSING | New | CALC-102 | IN
FA-B10 | NEW | B2B | Commission, price realisation, ECL provision | — | PROP | R-B2B | — | MISSING | New | CALC-103 | IN

## Legend_Summary
Field | Meaning
evidence_class | OBS = observed in authorized session; OBS-R = observed and arithmetically reconciled; OBS+PROP = observed entry point, proposed content; DOC = documented; DOC-F = documented formula; HIST = historical; PROP = proposed; NF = not found
disposition | IN / CONDITIONAL / NA / OMITTED (OMITTED = marketing function removed by Owner 2026-10-10; kept for traceability, not built)
status_before | Coverage of the Sellerboard item in the v0.1 SOW: COVERED / PARTIAL / MISSING / DIVERGENT
acceptance | All requirements remain UNACCEPTED until implementation evidence exists
v03_scope | Formula coverage rows: IN or OMITTED (marketing, v0.3)
version | v0.3 DRAFT — cutoff 2026-10-10; generated from engineering/scope_register.json
Requirements by disposition
CONDITIONAL | 22
IN | 147
OMITTED | 24
Formula coverage rows by v0.3 scope
IN | 111
OMITTED (marketing, v0.3) | 17
Requirements by release
R0 | 11
R1 | 80
R2 | 41
R3 | 20
R4 | 15
R5 | 17
— | 9
Sellerboard items by status (before v0.2)
COVERED | 22
PARTIAL | 44
MISSING | 39
DIVERGENT | 12