## README
06 — Cost & Traceability Model (INR) — in-house commerce-intelligence app (Rama / Phoenix) — v0.3
Purpose: editable planning model for build cost (labour by work package), CapEx-candidate / expense boundary, monthly OpEx, TCO (12/24/36 months), build-vs-buy vs Sellerboard, sensitivity and WP→release→feature traceability.
Version 0.3 — audit cutoff 2026-10-10 (baseline v0.1 cutoff 2026-09-10). Scope source: /engineering/scope_register.json (36 work packages WP-01..WP-39 with WP-18/19/21 retired, 11,180 h; releases R0–R5 with calendar_weeks; 31 connectors; 172 features). Regenerate with /engineering/build_cost_model.py. Price sources: /research/public_sources_apis.md.
ALL RATES AND ALLOWANCES ARE PLANNING ASSUMPTIONS, NOT QUOTES. No vendor, contractor or cloud provider has quoted these figures. Hourly rates are labelled assumptions for an Indian in-house / contract team; validate before approval.
Colour legend: BLUE text = input / assumption you may change; BLACK text = formula (do not overwrite); GREEN text = link to another sheet; YELLOW fill = key decision inputs (contingency %, capitalization approved %, benefit threshold).
How to change assumptions: edit BLUE cells on 'Assumptions' (rates, contingency, FTE capacity, FX, cloud, AI tokens, Sellerboard spend, scenario multipliers) and on 'WorkPackages' (hours per WP), and the category % inputs on 'Accounting_Boundary'. Every other sheet recalculates. Do not insert rows inside the rate table (rows referenced by VLOOKUP). To change scope, edit scope_register.json and re-run the build script.
Sheets: Assumptions · WorkPackages · Build_Summary · Capacity_Schedule · OpEx_Monthly (with applies_from_release) · TCO · Accounting_Boundary · Build_vs_Buy · Sensitivity · Traceability · Features_Ref (data extract used by Traceability counts) · Verification (key totals, LibreOffice-recalc verified) · Change_v02_v03 (v0.2 vs v0.3 bridge and the WPs that drove it).
Key conventions: hours × loaded rate = labour cost; cash TCO includes the 20% contingency as committed budget; it is shown separately in Build_Summary; 'Initial bounded release' = R0+R1 plus a pro-rata share of cross-cutting (ALL) WPs by hours; 'Full approved parity' = all WPs. Amortization is shown separately from cash and is never added to cash TCO. Capitalization is a CFO decision under Ind AS 38 / IAS 38 — default approved % is 0.
What changed in v0.3 (2026-10-10, Owner decisions): (1) marketing function omitted — WP-18 review requests, WP-19 PPC analytics and WP-21 PPC automation retired; WP-14 reduced to LTV/repeat customers (220 h); WP-20 safety framework reduced to repricer writes (280 h); ad spend is still read (WP-37, R1) as a cost line so net profit matches Sellerboard. (2) All markets — every Amazon marketplace (new WP-38, R2) and Walmart/eBay/TikTok Shop (WP-23 moved R5→R2, 600 h); ops connectors split to new WP-39 (R5). (3) Build with ChatGPT Codex; deploy on AWS. R2 is now 'All markets & marketplaces' (14 weeks); R4 'Pricing automation (conditional)' (6 weeks); R5 10 weeks. See Change_v02_v03.
Earlier — what changed in v0.2: R1 widened to 'India-first unified profit core' (14 weeks, was 10): WP-12 Shopify connector and WP-13 fee profiles moved R2→R1; new R1 WPs WP-31 (B2B sales), WP-32 (unified dashboard), WP-33 (mobile-first PWA shell), WP-34 (Sellerboard-compatible P&L + parallel run), WP-35 (Shopify cost completeness); new WP-36 (multi-entity consolidation) in R2; WP-24 reduced to 220 h. New OpEx line 'Courier/3PL data handling' (₹0 assumption, from R1). Sellerboard spend now 3 accounts on sellerboard.com + 1 Shopify store on sellerboard.io.
Excluded from all figures: ad spend, stock purchases, fulfilment fees, GST/taxes on services, office overhead, recruitment. SP-API fees: Amazon cancelled the planned fees 'at this time' (May 2026) → $0 planning assumption, monitor.
Sellerboard reference: sellerboard.com Business plan $39/mo observed (3 accounts); other .com plans $19–$79/mo per account. sellerboard.io (Shopify store, 1 store): plan NOT observed → $39/mo is an ASSUMPTION, labelled on Assumptions.

## Assumptions
Assumptions — all BLUE cells are planning assumptions, not quotes
Units: INR unless stated. Cutoff 2026-10-10. Scope register v0.3.
Loaded hourly rate by role (INR/h) | Value | Unit | Note
Solution architect | 3500 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Backend lead | 3000 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Backend | 2400 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Frontend | 2200 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Full-stack | 2400 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Integration eng | 2600 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Financial/data eng | 2600 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Data eng | 2400 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Product designer | 2000 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
QA/security | 1800 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
DevOps | 2400 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Delivery lead | 3000 | INR/h | Assumption — loaded (salary + overhead) India rate; not a quote
Delivery & capacity | Value | Unit | Note
Contingency % on labour | 20% | % | Committed budget in cash TCO; shown separately in Build_Summary
Nominal FTE capacity | 160 | h/month | Assumption
Productive factor | 0.75 | ratio | Share of nominal hours that is productive delivery
USD→INR | 84 | INR per USD | Assumption; refresh at approval date
Amortization period (capex-candidate) | 3 | years | Straight-line; shown separately from cash
Release calendar (from scope_register.json calendar_weeks) | Value | Unit | Note
R0 — Read-only pilot & foundations | 8 | weeks | Workspace, entities, connectors read-only, raw ledger, 90-day backfill, no operational writes
R1 — India-first unified profit core | 14 | weeks | One dashboard for Amazon.in + Shopify India + manual B2B: Sellerboard-compatible P&L, COGS, fees, expenses, B2B entry, reports, mobile-first UI, parallel-run reconciliation
R2 — All markets & marketplaces | 14 | weeks | UK/US/FR/DE entities and stores, every other Amazon marketplace (NA/EU/FE regions), Walmart US/CA/MX, eBay, TikTok Shop; multi-entity consolidation with FX & intercompany elimination; LTV & repeat customers; B2B receivables/export
R3 — Operations | 10 | weeks | Inventory planner, POs, suppliers, FBA/WFS shipments, reimbursement candidates (Money Back), alerts, automation safety framework
R4 — Pricing automation (conditional) | 6 | weeks | Repricer contract (simulation-first; writes only after approval, maker-checker, canary, kill switch)
R5 — Extended operations connectors & clients | 10 | weeks | ShipStation/Flexport/SFN/Veeqo/CJ connectors, PWA extras, browser extension, QuickBooks/Tally export & cashflow, optional AI explain layer
ALL — cross-cutting (sum of R0–R5) | 62 | weeks | Formula: sum of release weeks
Cloud hosting (monthly, INR) | Value | Unit | Note
Compute (app + workers) | 45000 | INR/mo | Assumption
Managed Postgres | 25000 | INR/mo | Assumption
Object storage | 8000 | INR/mo | Assumption
Jobs / queue | 10000 | INR/mo | Assumption
Egress | 5000 | INR/mo | Assumption
Observability | 12000 | INR/mo | Assumption
Backups / DR (cross-region copy to ap-south-2) | 6000 | INR/mo | Assumption
Security / landing zone (GuardDuty, Security Hub, Config, CloudTrail, WAF, KMS) | 18000 | INR/mo | Assumption
Ongoing staff / support | Value | Unit | Note
Support / maintenance FTE | 1 | FTE | Assumption — one engineer part-allocated
Support engineer loaded rate | 2400 | INR/h | Assumption
Support hours per FTE per month | 80 | h/mo | Assumption — 50% of nominal
Support monthly cost | 192000 | INR/mo | Formula = FTE × rate × hours
Provider / API version upgrade allowance | 20000 | INR/mo | Assumption — SP-API, Shopify, Ads API deprecation cycles
Security review (annual) | 300000 | INR/yr | Assumption — external pen-test / review
Optional native / browser-extension upkeep | 40000 | INR/mo | Assumption — set 0 if PWA-only (R5 scope)
Courier/3PL data handling | 0 | INR/mo | ASSUMPTION ₹0 — CSV/XLSX import of courier/3PL invoices (CON-32, WP-35) needs no paid API at cutoff; set a value if an aggregator/API fee is incurred. Applies from R1.
Software / API fees (monthly, INR) | Value | Unit | Note
Amazon SP-API | 0 | INR/mo | Amazon cancelled planned fees 'at this time' (May 2026) → $0; monitor (S35)
Amazon Ads API | 0 | INR/mo | No fee published
Shopify custom app | 0 | INR/mo | Custom app — no listing fee (applies from R1 in v0.2: WP-12 moved to R1)
Other tools (repo, CI, e-mail, monitoring SaaS) | 15000 | INR/mo | Assumption
ChatGPT Business seats with Codex (build team) | 12 | seats | Assumption — v0.3 build tool (DC-16); size to the actual team
ChatGPT Business Standard seat, monthly billing | 25 | USD/seat/mo | OpenAI Help Center, checked 2026-10-10 (S60): $25 monthly / $20 annual per seat, min 2 seats; Standard seats include Codex; usage limits may require Premium seats or credits
ChatGPT/Codex seats monthly | 25200 | INR/mo | Formula = seats × price × FX
AI consumption (Anthropic API, S47) — USD per million tokens | Value | Unit | Note
Input tokens / month (Fable 5.1) | 30 | M tokens | Assumption — explain layer, aggregates only
Output tokens / month (Fable 5.1) | 5 | M tokens | Assumption
Fable 5.1 input price | 10 | USD/MTok | Anthropic pricing at cutoff (S47)
Fable 5.1 output price | 50 | USD/MTok | Anthropic pricing at cutoff (S47)
Sonnet 5 fallback input tokens / month | 10 | M tokens | Assumption — cheaper fallback for routine explains
Sonnet 5 fallback output tokens / month | 2 | M tokens | Assumption
Sonnet 5 input price | 2 | USD/MTok | Anthropic pricing at cutoff
Sonnet 5 output price | 10 | USD/MTok | Anthropic pricing at cutoff
Haiku 4.5 input price (reference only) | 1 | USD/MTok | Not used in base case
Haiku 4.5 output price (reference only) | 5 | USD/MTok | Not used in base case
AI monthly cost (USD) | 590 | USD/mo | Formula
AI monthly cost (INR) | 49560 | INR/mo | Formula = USD × FX
One-time non-labour | Value | Unit | Note
Laptops / licences / domain / certificates | 400000 | INR one-time | Assumption
Training (user onboarding, playbooks) | 250000 | INR one-time | Assumption — excludes WP-29 labour
Migration | 0 | INR one-time | Handled by WP-29 hours (labour) — no separate allowance
Benefit & build-vs-buy | Value | Unit | Note
Monthly benefit threshold (INR) | 0 | INR/mo | Default 0 = unproven; enter only evidenced savings/margin gains
Sellerboard (sellerboard.com) spend per account | 39 | USD/mo | OBSERVED — Business plan $39/mo on sellerboard.com; .com plans $19–$79/mo
Sellerboard (sellerboard.com) accounts | 3 | accounts | 3 Amazon accounts on sellerboard.com (per owner, v0.2)
Sellerboard (sellerboard.io) spend per Shopify store | 39 | USD/mo | ASSUMPTION — sellerboard.io plan not observed at cutoff; $39/mo assumed equal to observed .com Business plan
Sellerboard (sellerboard.io) Shopify stores | 1 | stores | 1 Shopify store on sellerboard.io (per owner, v0.2)
Scenario multipliers (OpEx & build) | Value | Unit | Note
Low | 0.8 | × | Applied to OpEx and build in TCO
Base | 1 | ×
High | 1.3 | ×
Capitalization | Value | Unit | Note
Capitalization approved % | 0% | % | CFO decision under Ind AS 38 / IAS 38 — default 0 until criteria evidenced

## WorkPackages
Work packages — hours are BLUE inputs (from scope_register.json); rate via VLOOKUP on Assumptions; cost = hours × rate
WP | Name | Release | Owner role | Hours | Rate (INR/h) | Cost (INR) | Category | Dependencies | Calendar stage
WP-01 | Discovery, source audit, requirement freeze | R0 | Solution architect | 160 | 3500 | 560000 | Discovery | — | R0 — Read-only pilot & foundations (8 wk)
WP-02 | UX design system, atlas, accessibility baseline | R0 | Product designer | 240 | 2000 | 480000 | Design | WP-01 | R0 — Read-only pilot & foundations (8 wk)
WP-03 | Platform foundation: FastAPI, Postgres, queue, auth, RBAC, audit log, observability | R0 | Backend lead | 420 | 3000 | 1260000 | Backend | WP-01 | R0 — Read-only pilot & foundations (8 wk)
WP-04 | Workspace & entity model: legal entities, brands, stores, markets, currencies, timezones, periods | R0 | Backend | 220 | 2400 | 528000 | Backend | WP-03 | R0 — Read-only pilot & foundations (8 wk)
WP-05 | Amazon SP-API read connector: orders, finances, reports, settlements, inventory, inbound | R0 | Integration eng | 480 | 2600 | 1248000 | Connector core | WP-03, SP-API developer registration | R0 — Read-only pilot & foundations (8 wk)
WP-06 | Raw ledger, event/revision model, idempotent ingestion, replay, reconciliation | R0 | Backend | 320 | 2400 | 768000 | Backend | WP-03, WP-05 | R0 — Read-only pilot & foundations (8 wk)
WP-07 | Financial engine: fee taxonomy, COGS policies, allocations, FX, period close | R1 | Financial/data eng | 520 | 2600 | 1352000 | Financial engine | WP-06, WP-04 | R1 — India-first unified profit core (14 wk)
WP-08 | Profit dashboards: tiles, chart, P&L, trends, map, comparisons, custom tiles | R1 | Frontend | 480 | 2200 | 1056000 | Frontend | WP-07, WP-02 | R1 — India-first unified profit core (14 wk)
WP-09 | Products, COGS editor, landed-cost elements, imports/exports, sheets feed | R1 | Full-stack | 360 | 2400 | 864000 | Frontend | WP-07 | R1 — India-first unified profit core (14 wk)
WP-10 | Expenses: indirect, variable/tag-based, recognition schedules, allocations | R1 | Full-stack | 220 | 2400 | 528000 | Backend | WP-07 | R1 — India-first unified profit core (14 wk)
WP-11 | Reports & exports: grains, CSV/XLSX, scheduling, Claude-ready bundles | R1 | Backend | 260 | 2400 | 624000 | Backend | WP-07, WP-08 | R1 — India-first unified profit core (14 wk)
WP-12 | Shopify connector: Admin GraphQL bulk, webhooks, Payments payouts, protected data | R1 | Integration eng | 400 | 2600 | 1040000 | Connector core | WP-06, Shopify read_all_orders approval | R1 — India-first unified profit core (14 wk)
WP-13 | Shipping/pick-pack/payment-fee profiles; Shopify revenue composition; MCF/WFS dedup; multichannel economics | R1 | Financial/data eng | 280 | 2600 | 728000 | Financial engine | WP-12, WP-07 | R1 — India-first unified profit core (14 wk)
WP-14 | LTV, repeat customers, cohorts & replenishment cycles (no ad attribution, no campaign analytics) | R2 | Data eng | 220 | 2400 | 528000 | Financial engine | WP-12, WP-07 (no ad attribution in v0.3) | R2 — All markets & marketplaces (14 wk)
WP-15 | Inventory: planner, velocity, reorder, POs, suppliers, shipments, prep, reconciliation | R3 | Full-stack | 480 | 2400 | 1152000 | Backend | WP-05, WP-09 | R3 — Operations (10 wk)
WP-16 | Money Back: reimbursement candidates, eligibility, deadlines, evidence packs, realization | R3 | Full-stack | 260 | 2400 | 624000 | Backend | WP-05, WP-07 | R3 — Operations (10 wk)
WP-17 | Alerts engine: rules, dedup, priorities, routing, escalation | R3 | Backend | 240 | 2400 | 576000 | Automation | WP-06 | R3 — Operations (10 wk)
WP-20 | Automation safety framework for repricer writes: simulation, maker-checker, canary, kill switch, audit, replay | R3 | Backend | 280 | 2400 | 672000 | Automation | WP-17, WP-06 | R3 — Operations (10 wk)
WP-22 | Repricer contract, floors/ROI, price history, observation, simulation (writes conditional) | R4 | Full-stack | 300 | 2400 | 720000 | Automation | WP-20, WP-07 | R4 — Pricing automation (conditional) (6 wk)
WP-23 | Marketplace connectors: Walmart (Marketplace, WFS, Walmart Connect/SEM spend read), eBay, TikTok Shop — orders, fees, settlements, returns, inventory; compat P&L mapping | R2 | Integration eng | 600 | 2600 | 1560000 | Connector extended | WP-06, WP-07, WP-13, WP-38; Walmart/eBay/TikTok Shop developer access | R2 — All markets & marketplaces (14 wk)
WP-24 | Native-feel PWA extras (offline, push), browser extension, localization, accessibility audit | R5 | Frontend | 220 | 2200 | 484000 | Frontend | WP-08, WP-33 | R5 — Extended operations connectors & clients (10 wk)
WP-25 | QuickBooks/accounting export, cashflow, settlement bridge | R5 | Full-stack | 200 | 2400 | 480000 | Connector extended | WP-07, WP-11 | R5 — Extended operations connectors & clients (10 wk)
WP-26 | Optional Anthropic API explain layer (aggregates only), MCP-style read connector | R5 | Backend | 160 | 2400 | 384000 | Connector extended | WP-11, Anthropic API key | R5 — Extended operations connectors & clients (10 wk)
WP-27 | QA, security review, performance, UAT support | ALL | QA/security | 640 | 1800 | 1152000 | QA-security | Continuous (all releases) | Cross-cutting — all releases
WP-28 | DevOps, environments, CI/CD, backups, runbooks | ALL | DevOps | 320 | 2400 | 768000 | DevOps | Continuous (all releases) | Cross-cutting — all releases
WP-29 | Migration from Sellerboard exports, historical COGS, training, documentation | ALL | Data eng | 240 | 2400 | 576000 | Migration | WP-09, Sellerboard exports | Cross-cutting — all releases
WP-30 | Delivery leadership, change control, approvals | ALL | Delivery lead | 400 | 3000 | 1200000 | Leadership | Continuous (all releases) | Cross-cutting — all releases
WP-31 | B2B sales module: customer master, manual invoice entry, GST/HSN, credit notes, import, receivables, export invoices | R1 | Full-stack | 520 | 2400 | 1248000 | Backend | WP-04, WP-07 (GST/HSN masters) | R1 — India-first unified profit core (14 wk)
WP-32 | Unified dashboard: channel dimension (Amazon/Shopify/B2B/…), account & channel filters, summary tiles, channel mix | R1 | Financial/data eng | 280 | 2600 | 728000 | Financial engine | WP-07, WP-08, WP-12, WP-31 | R1 — India-first unified profit core (14 wk)
WP-33 | Mobile-first responsive dashboards & installable PWA shell (tiles, P&L, alerts, B2B entry on phone) | R1 | Frontend | 200 | 2200 | 440000 | Frontend | WP-02, WP-08 | R1 — India-first unified profit core (14 wk)
WP-34 | Sellerboard-compatible P&L mode, calculation lineage drawer, data freshness/completeness, parallel-run reconciliation | R1 | Financial/data eng | 220 | 2600 | 572000 | Financial engine | WP-07, WP-29 (Sellerboard exports) | R1 — India-first unified profit core (14 wk)
WP-35 | Shopify cost completeness: courier/3PL actual costs, RTO/COD, gateway fee table, returns costs, order inclusion rules | R1 | Integration eng | 200 | 2600 | 520000 | Connector core | WP-12, WP-13; courier/3PL export (CON-32) | R1 — India-first unified profit core (14 wk)
WP-36 | Multi-entity consolidation: entity hierarchy, FX policies, intercompany elimination, budget/targets | R2 | Financial/data eng | 180 | 2600 | 468000 | Financial engine | WP-04, WP-07 | R2 — All markets & marketplaces (14 wk)
WP-37 | Ad-spend read connectors for profit only: Amazon Ads spend by campaign/product/day, Google Ads and Meta spend; CSV import for any other ad platform (no campaign analytics, no writes) | R1 | Integration eng | 260 | 2600 | 676000 | Connector core | WP-03, WP-06; Amazon Ads API access (read), Google/Meta OAuth | R1 — India-first unified profit core (14 wk)
WP-38 | All Amazon marketplaces: NA/EU/FE regions, marketplace master (currency, timezone, tax regime, fee codes), multi-region auth & rate limits, per-marketplace fixtures | R2 | Integration eng | 240 | 2600 | 624000 | Connector core | WP-05, WP-07, WP-04 (marketplace master) | R2 — All markets & marketplaces (14 wk)
WP-39 | Operations connectors: ShipStation, Flexport/SFN, Veeqo, CJ Dropshipping (read-only) | R5 | Integration eng | 160 | 2600 | 416000 | Connector extended | WP-06, WP-13; per-connector access | R5 — Extended operations connectors & clients (10 wk)
TOTAL |  |  |  | 11180 |  | 27604000 |  | OK — matches register 11,180 h
Category list (used by other sheets): Discovery, Design, Backend, Frontend, Financial engine, Connector core, Connector extended, Automation, QA-security, DevOps, Migration, Training, Leadership
Note: 'Training' category has no WP (training is a one-time non-labour allowance on Assumptions); WP-29 covers migration + documentation labour. Categories and dependencies are planning classifications held in build_cost_model.py (not in the register).

## Build_Summary
Build summary — by release, initial bounded release vs full parity, by category
All INR. Contingency = labour × contingency %.
Release | Hours | Labour cost | Contingency | Total incl. contingency | Note
R0 — Read-only pilot & foundations | 1840 | 4844000 | 968800 | 5812800 | Workspace, entities, connectors read-only, raw ledger, 90-day backfill, no operational wri
R1 — India-first unified profit core | 4200 | 10376000 | 2075200 | 12451200 | One dashboard for Amazon.in + Shopify India + manual B2B: Sellerboard-compatible P&L, COGS
R2 — All markets & marketplaces | 1240 | 3180000 | 636000 | 3816000 | UK/US/FR/DE entities and stores, every other Amazon marketplace (NA/EU/FE regions), Walmar
R3 — Operations | 1260 | 3024000 | 604800 | 3628800 | Inventory planner, POs, suppliers, FBA/WFS shipments, reimbursement candidates (Money Back
R4 — Pricing automation (conditional) | 300 | 720000 | 144000 | 864000 | Repricer contract (simulation-first; writes only after approval, maker-checker, canary, ki
R5 — Extended operations connectors & clients | 740 | 1764000 | 352800 | 2116800 | ShipStation/Flexport/SFN/Veeqo/CJ connectors, PWA extras, browser extension, QuickBooks/Ta
ALL | 1600 | 3696000 | 739200 | 4435200 | Cross-cutting WPs (QA, DevOps, migration, leadership)
TOTAL — Full approved parity (all WPs) | 11180 | 27604000 | 5520800 | 33124800
Initial bounded release (R0 + R1 + pro-rata share of ALL WPs by hours)
Pro-rata factor = (hours R0 + hours R1) ÷ (hours R0..R5, excluding ALL) | 63.05%
Component | Hours | Labour cost | Contingency | Total incl. contingency | Formula
R0 + R1 direct | 6040 | 15220000 | 3044000 | 18264000 | Sum of R0 and R1 rows
Pro-rata share of ALL WPs | 1008.7683 | 2330254.6973 | 466050.9395 | 2796305.6367 | ALL row × pro-rata factor
INITIAL BOUNDED RELEASE — total | 7048.7683 | 17550254.6973 | 3510050.9395 | 21060305.6367
FULL APPROVED PARITY — total | 11180 | 27604000 | 5520800 | 33124800
Initial as % of full |  | 63.58%
By category
Category | Hours | Labour cost | Contingency | Total incl. contingency | Share of labour
Discovery | 160 | 560000 | 112000 | 672000 | 2.029%
Design | 240 | 480000 | 96000 | 576000 | 1.739%
Backend | 2700 | 6732000 | 1346400 | 8078400 | 24.39%
Frontend | 1260 | 2844000 | 568800 | 3412800 | 10.3%
Financial engine | 1700 | 4376000 | 875200 | 5251200 | 15.85%
Connector core | 1580 | 4108000 | 821600 | 4929600 | 14.88%
Connector extended | 1120 | 2840000 | 568000 | 3408000 | 10.29%
Automation | 820 | 1968000 | 393600 | 2361600 | 7.129%
QA-security | 640 | 1152000 | 230400 | 1382400 | 4.173%
DevOps | 320 | 768000 | 153600 | 921600 | 2.782%
Migration | 240 | 576000 | 115200 | 691200 | 2.087%
Training | 0 | 0 | 0 | 0 | 0%
Leadership | 400 | 1200000 | 240000 | 1440000 | 4.347%
TOTAL (check = full parity) | 11180 | 27604000 | 5520800 | 33124800 | OK — reconciles

## Capacity_Schedule
Capacity schedule — FTE by role per release = hours ÷ (nominal h/mo × productive factor) ÷ months in release
Months = calendar weeks × 12/52 (weeks from scope_register.json via Assumptions). FTE > 1.0 flagged (needs more than one person of that role, or a longer calendar).
Productive hours per FTE-month | 120
Role | R0 | R1 | R2 | R3 | R4 | R5 | ALL | Flag | R0 flag | R1 flag | R2 flag | R3 flag | R4 flag | R5 flag | ALL flag
Calendar weeks | 8 | 14 | 14 | 10 | 6 | 10 | 62
Months | 1.8462 | 3.2308 | 3.2308 | 2.3077 | 1.3846 | 2.3077 | 14.3077
Solution architect | 0.72222 | 0 | 0 | 0 | 0 | 0 | 0
Backend lead | 1.8958 | 0 | 0 | 0 | 0 | 0 | 0 |  | >1 FTE
Backend | 2.4375 | 0.67063 | 0 | 1.8778 | 0 | 0.57778 | 0 |  | >1 FTE |  |  | >1 FTE
Frontend | 0 | 1.754 | 0 | 0 | 0 | 0.79444 | 0 |  |  | >1 FTE
Full-stack | 0 | 2.8373 | 0 | 2.6722 | 1.8056 | 0.72222 | 0 |  |  | >1 FTE |  | >1 FTE | >1 FTE
Integration eng | 2.1667 | 2.2183 | 2.1667 | 0 | 0 | 0.57778 | 0 |  | >1 FTE | >1 FTE | >1 FTE
Financial/data eng | 0 | 3.3532 | 0.46429 | 0 | 0 | 0 | 0 |  |  | >1 FTE
Data eng | 0 | 0 | 0.56746 | 0 | 0 | 0 | 0.13978
Product designer | 1.0833 | 0 | 0 | 0 | 0 | 0 | 0 |  | >1 FTE
QA/security | 0 | 0 | 0 | 0 | 0 | 0 | 0.37276
DevOps | 0 | 0 | 0 | 0 | 0 | 0 | 0.18638
Delivery lead | 0 | 0 | 0 | 0 | 0 | 0 | 0.23297
Total FTE (role-sum) | 8.3056 | 10.8333 | 3.1984 | 4.55 | 1.8056 | 2.6722 | 0.9319
Reading: a value of 1.4 for 'Integration eng' in R1 means the R1 calendar needs 1.4 integration engineers at 120 productive h/month, or the release stretches. ALL column spreads cross-cutting WPs across the full programme (sum of release weeks). v0.3: R1 is 14 weeks and carries WP-07..13, WP-31..35 and WP-37; R2 (14 weeks) carries WP-14, WP-23, WP-36, WP-38.

## OpEx_Monthly
Monthly operating cost — line items from Assumptions; low / base / high = scenario multipliers
INR. Annual = monthly × 12.
Line item | Applies from release | Monthly (base) | Monthly low | Monthly high | Annual base | Annual low | Annual high | Source
Cloud — compute | R0 | 45000 | 36000 | 58500 | 540000 | 432000 | 702000 | Assumptions sheet
Cloud — managed Postgres | R0 | 25000 | 20000 | 32500 | 300000 | 240000 | 390000 | Assumptions sheet
Cloud — object storage | R0 | 8000 | 6400 | 10400 | 96000 | 76800 | 124800 | Assumptions sheet
Cloud — jobs / queue | R0 | 10000 | 8000 | 13000 | 120000 | 96000 | 156000 | Assumptions sheet
Cloud — egress | R0 | 5000 | 4000 | 6500 | 60000 | 48000 | 78000 | Assumptions sheet
Cloud — observability | R0 | 12000 | 9600 | 15600 | 144000 | 115200 | 187200 | Assumptions sheet
Cloud — backups / DR | R0 | 6000 | 4800 | 7800 | 72000 | 57600 | 93600 | Assumptions sheet
Cloud — security / landing zone | R0 | 18000 | 14400 | 23400 | 216000 | 172800 | 280800 | Assumptions sheet — NEW v0.2 (handoff review C-28)
Support / maintenance staff | R1 | 192000 | 153600 | 249600 | 2304000 | 1843200 | 2995200 | Assumptions sheet
Provider / API upgrade allowance | R0 | 20000 | 16000 | 26000 | 240000 | 192000 | 312000 | Assumptions sheet
Security review (annual ÷ 12) | R0 | 25000 | 20000 | 32500 | 300000 | 240000 | 390000 | Assumptions sheet
Software / API — SP-API | R0 | 0 | 0 | 0 | 0 | 0 | 0 | Assumptions sheet
Software / API — Ads API (spend read) | R1 | 0 | 0 | 0 | 0 | 0 | 0 | Assumptions sheet — v0.3: spend read from R1 (WP-37); no PPC analytics
Software / API — Shopify custom app | R1 | 0 | 0 | 0 | 0 | 0 | 0 | Assumptions sheet — v0.2: R1 (WP-12 moved R2→R1)
Software / API — other tools | R0 | 15000 | 12000 | 19500 | 180000 | 144000 | 234000 | Assumptions sheet
Software / API — ChatGPT/Codex seats (build tool) | R0 | 25200 | 20160 | 32760 | 302400 | 241920 | 393120 | Assumptions sheet — NEW v0.3 (DC-16; review finding v0.3-13)
Courier/3PL data handling | R1 | 0 | 0 | 0 | 0 | 0 | 0 | Assumptions sheet — NEW v0.2; ₹0 ASSUMPTION (CON-32 / WP-35)
AI consumption (Anthropic) | R5 | 49560 | 39648 | 64428 | 594720 | 475776 | 773136 | Assumptions sheet
Optional native / extension upkeep | R5 | 40000 | 32000 | 52000 | 480000 | 384000 | 624000 | Assumptions sheet
TOTAL OpEx — full parity (all lines) |  | 495760 | 396608 | 644488 | 5949120 | 4759296 | 7733856
TOTAL OpEx — initial release (lines applicable ≤ R1) |  | 406200 | 324960 | 528060 | 4874400 | 3899520 | 6336720 | Excludes AI consumption and native/extension upkeep (start R5); includes Ads API spend read (₹0), Shopify app and Courier/3PL line (R1)
of which cloud subtotal |  | 129000
'Applies from release' (blue) drives which lines count toward the initial-release (R0+R1) OpEx and phased Year-1 on the TCO sheet.

## TCO
Total cost of ownership — cash basis; amortization shown as separate memo line (NOT added)
INR. Build = labour + contingency + one-time non-labour + training. Cash TCO includes the 20% contingency as committed budget; it is shown separately in Build_Summary. OpEx from OpEx_Monthly (initial-release horizons use only lines applicable ≤R1). Low/base/high = scenario multipliers on Assumptions.
Inputs pulled
Initial bounded release build (labour + contingency) | 21060305.6367
Full approved parity build (labour + contingency) | 33124800
One-time non-labour + training | 650000
Monthly OpEx (base) — full parity | 495760
Monthly OpEx (base) — initial release (lines ≤R1) | 406200
Scenario multipliers → | 0.8 | 1 | 1.3
A. Initial bounded release (R0+R1 + pro-rata ALL) — all build cash in month 0; OpEx lines ≤R1 only
Horizon | Low | Base | High | Formula
12-month cash TCO | 21267764.5094 | 26584705.6367 | 34560117.3278 | (build + one-time) × mult + monthly OpEx × 12 × mult
24-month cash TCO | 25167284.5094 | 31459105.6367 | 40896837.3278 | (build + one-time) × mult + monthly OpEx × 24 × mult
36-month cash TCO | 29066804.5094 | 36333505.6367 | 47233557.3278 | (build + one-time) × mult + monthly OpEx × 36 × mult
B. Full approved parity — all build cash in month 0; full OpEx
Horizon | Low | Base | High | Formula
12-month cash TCO | 31779136 | 39723920 | 51641096 | (build + one-time) × mult + monthly OpEx × 12 × mult
24-month cash TCO | 36538432 | 45673040 | 59374952 | (build + one-time) × mult + monthly OpEx × 24 × mult
36-month cash TCO | 41297728 | 51622160 | 67108808 | (build + one-time) × mult + monthly OpEx × 36 × mult
C. Phased full parity — R0–R1 in year 1, R2–R3 in year 2, R4–R5 in year 3 (ALL WPs pro-rata by hours per year)
Year | Build cash in year (base) | OpEx in year (base) | Cumulative cash TCO (base) | Formula
Year 1 (R0+R1) | 21710305.6367 | 4874400 | 26584705.6367 | release totals incl. contingency + ALL × hours share + one-time; initial-release OpEx (≤R1) × 12
Year 2 (R2+R3) | 8602211.2735 | 4874400 | 40061316.9102 | release totals incl. contingency + ALL × hours share; OpEx lines ≤R1 × 12 (R5-only lines not yet live)
Year 3 (R4+R5) | 3462283.0898 | 5949120 | 49472720 | release totals incl. contingency + ALL × hours share; full OpEx × 12
Check: phased build sum = full parity build + one-time (phased TCO < B because Years 1–2 OpEx use the ≤R1 subset; phasing is illustrative — calendar is 62 weeks if sequential) | 33774800 |  |  | OK — reconciles
Phased 36-month cash TCO — low / base / high | 39578176 | 49472720 | 64314536
MEMO — amortization (NOT cash, NOT added to TCO above)
Horizon | Approved CapEx | Cumulative amortization | Net book value | Note
12 months | 0 | 0 | 0 | Straight-line over Assumptions amortization years, on approved CapEx only (default 0)
24 months | 0 | 0 | 0 | Straight-line over Assumptions amortization years, on approved CapEx only (default 0)
36 months | 0 | 0 | 0 | Straight-line over Assumptions amortization years, on approved CapEx only (default 0)

## Accounting_Boundary
Accounting boundary — CapEx-candidate (development) vs expensed, by WP category
Candidate-qualifying % is a judgement INPUT per category (blue). Actual capitalization requires CFO approval; default approved % = 0.
Category | Hours | Labour cost | Candidate-qualifying % | Candidate-qualifying cost | Expensed cost | Rationale (planning judgement — not accounting advice)
Discovery | 160 | 560000 | 0% | 0 | 560000 | Research phase — expensed (IAS 38.54)
Design | 240 | 480000 | 80% | 384000 | 96000 | UX design of the application — development; 20% exploratory
Backend | 2700 | 6732000 | 90% | 6058800 | 673200 | Development of the asset; 10% spikes / rework (incl. WP-31 B2B module)
Frontend | 1260 | 2844000 | 90% | 2559600 | 284400 | Development (incl. WP-33 mobile-first PWA shell)
Financial engine | 1700 | 4376000 | 90% | 3938400 | 437600 | Development (incl. WP-32, WP-34, WP-36)
Connector core | 1580 | 4108000 | 90% | 3697200 | 410800 | Development (incl. WP-35 Shopify cost completeness)
Connector extended | 1120 | 2840000 | 90% | 2556000 | 284000 | Development (R5)
Automation | 820 | 1968000 | 90% | 1771200 | 196800 | Development
QA-security | 640 | 1152000 | 50% | 576000 | 576000 | Testing during development qualifies; UAT support & security review share expensed
DevOps | 320 | 768000 | 60% | 460800 | 307200 | Environment build qualifies; run/operate share expensed
Migration | 240 | 576000 | 0% | 0 | 576000 | Data conversion & documentation — expensed
Training | 0 | 0 | 0% | 0 | 0 | Training — expensed (IAS 38.69)
Leadership | 400 | 1200000 | 30% | 360000 | 840000 | Directly attributable PM share; change control / approvals expensed
TOTAL labour | 11180 | 27604000 | 81.01% | 22362000 | 5242000 | OK — reconciles to Build_Summary
Resulting classification (full parity)
Capitalization approved % |  | 0% |  |  |  | Set on Assumptions after CFO review; default 0
CapEx (approved) = candidate-qualifying × approved % |  | 0
Expense = total labour − CapEx approved |  | 27604000
Contingency reserve (committed budget; classified when drawn) |  | 5520800
One-time non-labour (laptops/licences) — expensed or PPE per policy |  | 400000
Training — expensed |  | 250000
Amortization (only on approved CapEx)
Amortization years |  | 3
Annual straight-line amortization |  | 0
Monthly amortization |  | 0
Ind AS 38 / IAS 38 (para 57) — development costs may be capitalized only when ALL six criteria are demonstrated:
1) technical feasibility of completing the asset; 2) intention to complete and use it; 3) ability to use it; 4) how it will generate probable future economic benefits;
5) availability of adequate technical, financial and other resources to complete; 6) ability to measure attributable expenditure reliably.
Research-phase (discovery), training, data migration/conversion, and post-implementation maintenance are expensed. Percentages above are planning judgements for a CFO / auditor review, not accounting advice.
Cash TCO on the TCO sheet is unaffected by this classification; amortization is shown there as a separate memo line.

## Build_vs_Buy
Build vs buy — existing Sellerboard spend vs in-house app OpEx; payback on benefit threshold
Benefit default 0 → payback shows 'N/A (benefit unproven)'. Excluded from both sides: ad spend, stock, fulfilment, GST.
Item | Monthly (INR) | Annual (INR) | Note
Sellerboard (sellerboard.com) = accounts × USD/mo × FX | 9828 | 117936 | OBSERVED: $39/mo Business plan on sellerboard.com; 3 accounts
Sellerboard (sellerboard.io) = Shopify stores × USD/mo × FX | 3276 | 39312 | ASSUMPTION: sellerboard.io plan unknown → $39/mo assumed; 1 Shopify store
Sellerboard spend — total | 13104 | 157248
In-house app OpEx (base) — full parity | 495760 | 5949120 | From OpEx_Monthly
Monthly OpEx delta (app − Sellerboard) | 482656 | 5791872 | Positive = app costs more to run than Sellerboard
Sellerboard spend as % of app OpEx | 2.643%
Payback
Monthly benefit threshold (INR) — from Assumptions | 0 |  | Default 0 = unproven. Enter only evidenced margin gains / savings.
Net monthly benefit = benefit − OpEx delta | -482656
Payback (months) — initial bounded release | N/A (benefit unproven) |  | Formula: (build incl. contingency + one-time) ÷ net monthly benefit
Payback (months) — full parity | N/A (benefit unproven) |  | Formula: (build incl. contingency + one-time) ÷ net monthly benefit
Monthly benefit needed for 36-month payback (full parity) | 1420844.8889 |  | Reference: benefit that would be required, not a forecast
Excluded costs on both sides: advertising spend, inventory/stock purchases, fulfilment & shipping fees, marketplace commissions, GST, office overhead.
Sellerboard replacement is not cost-driven at these figures: the app's OpEx alone exceeds the combined sellerboard.com + sellerboard.io subscription many times over; the case rests on evidenced benefits (data ownership, India-first fee taxonomy, unified Amazon + Shopify + B2B view, automation with maker-checker) that this sheet treats as unproven until entered.

## Sensitivity
Sensitivity — effect on 36-month cash TCO (full parity, base scenario)
Each row varies one driver from the base; all formulas reference TCO and OpEx sheets. Multipliers in column B are BLUE inputs.
Base 36-month TCO (full parity, base) | 51622160
Labour incl. contingency (full parity) | 33124800
Cloud monthly (base) | 129000
AI monthly (base) | 49560
Case | Multiplier | Δ 36-month TCO | 36-month TCO | Δ % | Mechanism
Hourly rates −20% | 0.8 | -6624960 | 44997200 | -12.83% | labour × (mult − 1)
Hourly rates +20% | 1.2 | 6624960 | 58247120 | 12.83% | labour × (mult − 1)
Hours −30% | 0.7 | -9937440 | 41684720 | -19.25% | labour × (mult − 1)
Hours +30% | 1.3 | 9937440 | 61559600 | 19.25% | labour × (mult − 1)
Cloud −40% | 0.6 | -1857600 | 49764560 | -3.598% | cloud monthly × 36 × (mult − 1)
Cloud +40% | 1.4 | 1857600 | 53479760 | 3.598% | cloud monthly × 36 × (mult − 1)
AI tokens ×0.5 | 0.5 | -892080 | 50730080 | -1.728% | AI monthly × 36 × (mult − 1)
AI tokens ×3 | 3 | 3568320 | 55190480 | 6.912% | AI monthly × 36 × (mult − 1)
Combined worst case (rates +20%, hours +30%, cloud +40%, AI ×3) |  | 23975808 | 75597968 | 46.44% | Multiplicative on labour (rate × hours multiplier cells); additive on OpEx drivers — references the multiplier cells above
Note: rate and hours cases scale labour and its contingency together (contingency is a % of labour).

## Traceability
Traceability — WP → release → features (count from Features_Ref) → calculations / connectors
Feature counts are COUNTIF formulas over Features_Ref (WP column). Calc/connector lists are text extracted from scope_register.json (union over the WP's features).
WP | Name | Release | Features (count) | Hours | Calculations (CALC ids) | Connectors (CON ids) | Cost (INR)
WP-01 | Discovery, source audit, requirement freeze | R0 | 0 | 160 | — | — | 560000
WP-02 | UX design system, atlas, accessibility baseline | R0 | 0 | 240 | — | — | 480000
WP-03 | Platform foundation: FastAPI, Postgres, queue, auth, RBAC, audit log, observability | R0 | 4 | 420 | — | — | 1260000
WP-04 | Workspace & entity model: legal entities, brands, stores, markets, currencies, timezones, periods | R0 | 3 | 220 | CALC-026 | — | 528000
WP-05 | Amazon SP-API read connector: orders, finances, reports, settlements, inventory, inbound | R0 | 1 | 480 | — | CON-01 | 1248000
WP-06 | Raw ledger, event/revision model, idempotent ingestion, replay, reconciliation | R0 | 2 | 320 | — | — | 768000
WP-07 | Financial engine: fee taxonomy, COGS policies, allocations, FX, period close | R1 | 10 | 520 | CALC-003, CALC-004, CALC-007, CALC-009, CALC-023, CALC-024, CALC-025, CALC-053, CALC-054, CALC-067, CALC-079, CALC-080, CALC-082, CALC-109 | CON-01 | 1352000
WP-08 | Profit dashboards: tiles, chart, P&L, trends, map, comparisons, custom tiles | R1 | 18 | 480 | CALC-001, CALC-002, CALC-003, CALC-010, CALC-012, CALC-013, CALC-014, CALC-015, CALC-016, CALC-017, CALC-018, CALC-019, CALC-026, CALC-030, CALC-031, CALC-045, CALC-048, CALC-050, CALC-051, CALC-052, CALC-053, CALC-054, CALC-059, CALC-072, CALC-081, CALC-085, CALC-101, CALC-108, CALC-111 | CON-01 | 1056000
WP-09 | Products, COGS editor, landed-cost elements, imports/exports, sheets feed | R1 | 8 | 360 | CALC-005, CALC-006, CALC-007, CALC-008, CALC-066, CALC-078, CALC-087 | CON-23 | 864000
WP-10 | Expenses: indirect, variable/tag-based, recognition schedules, allocations | R1 | 2 | 220 | CALC-011, CALC-024, CALC-091 | — | 528000
WP-11 | Reports & exports: grains, CSV/XLSX, scheduling, Claude-ready bundles | R1 | 4 | 260 | CALC-035, CALC-083 | — | 624000
WP-12 | Shopify connector: Admin GraphQL bulk, webhooks, Payments payouts, protected data | R1 | 2 | 400 | — | CON-05, CON-06 | 1040000
WP-13 | Shipping/pick-pack/payment-fee profiles; Shopify revenue composition; MCF/WFS dedup; multichannel economics | R1 | 6 | 280 | CALC-020, CALC-021, CALC-022, CALC-047, CALC-052, CALC-076 | CON-05, CON-06, CON-32 | 728000
WP-14 | LTV, repeat customers, cohorts & replenishment cycles (no ad attribution, no campaign analytics) | R2 | 5 | 220 | CALC-033, CALC-034, CALC-035, CALC-036, CALC-084, CALC-106 | CON-05, CON-29 | 528000
WP-15 | Inventory: planner, velocity, reorder, POs, suppliers, shipments, prep, reconciliation | R3 | 11 | 480 | CALC-037, CALC-038, CALC-039, CALC-040, CALC-062, CALC-063, CALC-064, CALC-065, CALC-086, CALC-089, CALC-092 | CON-01, CON-05, CON-16 | 1152000
WP-16 | Money Back: reimbursement candidates, eligibility, deadlines, evidence packs, realization | R3 | 5 | 260 | CALC-044, CALC-068, CALC-069, CALC-070, CALC-071 | CON-01 | 624000
WP-17 | Alerts engine: rules, dedup, priorities, routing, escalation | R3 | 3 | 240 | CALC-043 | CON-01 | 576000
WP-20 | Automation safety framework for repricer writes: simulation, maker-checker, canary, kill switch, audit, replay | R3 | 2 | 280 | CALC-041, CALC-075 | — | 672000
WP-22 | Repricer contract, floors/ROI, price history, observation, simulation (writes conditional) | R4 | 3 | 300 | CALC-041 | CON-01, CON-25 | 720000
WP-23 | Marketplace connectors: Walmart (Marketplace, WFS, Walmart Connect/SEM spend read), eBay, TikTok Shop — orders, fees, settlements, returns, inventory; compat P&L mapping | R2 | 14 | 600 | CALC-067, CALC-079, CALC-114 | CON-05, CON-07, CON-11, CON-16, CON-17, CON-18, CON-29 | 1560000
WP-24 | Native-feel PWA extras (offline, push), browser extension, localization, accessibility audit | R5 | 3 | 220 | — | CON-01 | 484000
WP-25 | QuickBooks/accounting export, cashflow, settlement bridge | R5 | 3 | 200 | CALC-027, CALC-073 | CON-01, CON-27 | 480000
WP-26 | Optional Anthropic API explain layer (aggregates only), MCP-style read connector | R5 | 2 | 160 | — | CON-28 | 384000
WP-27 | QA, security review, performance, UAT support | ALL | 0 | 640 | — | — | 1152000
WP-28 | DevOps, environments, CI/CD, backups, runbooks | ALL | 0 | 320 | — | — | 768000
WP-29 | Migration from Sellerboard exports, historical COGS, training, documentation | ALL | 0 | 240 | — | — | 576000
WP-30 | Delivery leadership, change control, approvals | ALL | 0 | 400 | — | — | 1200000
WP-31 | B2B sales module: customer master, manual invoice entry, GST/HSN, credit notes, import, receivables, export invoices | R1 | 11 | 520 | CALC-026, CALC-092, CALC-093, CALC-094, CALC-095, CALC-096, CALC-097, CALC-098, CALC-099, CALC-100, CALC-102, CALC-103 | CON-33 | 1248000
WP-32 | Unified dashboard: channel dimension (Amazon/Shopify/B2B/…), account & channel filters, summary tiles, channel mix | R1 | 2 | 280 | CALC-050, CALC-051, CALC-097, CALC-100, CALC-101, CALC-110 | CON-01, CON-05 | 728000
WP-33 | Mobile-first responsive dashboards & installable PWA shell (tiles, P&L, alerts, B2B entry on phone) | R1 | 1 | 200 | — | — | 440000
WP-34 | Sellerboard-compatible P&L mode, calculation lineage drawer, data freshness/completeness, parallel-run reconciliation | R1 | 4 | 220 | CALC-043, CALC-050, CALC-051, CALC-052 | — | 572000
WP-35 | Shopify cost completeness: courier/3PL actual costs, RTO/COD, gateway fee table, returns costs, order inclusion rules | R1 | 5 | 200 | CALC-022, CALC-077, CALC-090, CALC-104, CALC-105 | CON-05, CON-06, CON-32 | 520000
WP-36 | Multi-entity consolidation: entity hierarchy, FX policies, intercompany elimination, budget/targets | R2 | 1 | 180 | CALC-107 | — | 468000
WP-37 | Ad-spend read connectors for profit only: Amazon Ads spend by campaign/product/day, Google Ads and Meta spend; CSV import for any other ad platform (no campaign analytics, no writes) | R1 | 4 | 260 | CALC-059, CALC-079, CALC-091 | CON-02, CON-08, CON-09 | 676000
WP-38 | All Amazon marketplaces: NA/EU/FE regions, marketplace master (currency, timezone, tax regime, fee codes), multi-region auth & rate limits, per-marketplace fixtures | R2 | 2 | 240 | CALC-026, CALC-067, CALC-092, CALC-113 | CON-01 | 624000
WP-39 | Operations connectors: ShipStation, Flexport/SFN, Veeqo, CJ Dropshipping (read-only) | R5 | 4 | 160 | — | CON-19, CON-20, CON-21, CON-22 | 416000
TOTAL |  |  | 145 | 11180 |  |  | 27604000
Features in register (COUNTA of Features_Ref) |  |  | 172
Features without WP mapping (NA + OMITTED v0.3) |  |  | 27
Feature→WP links counted (= TOTAL above) |  |  | 145
Register feature count (scope_register.json v0.3) |  |  | 172
Check: COUNTA = register and links + unmapped = features |  |  | OK
Features by release (COUNTIF over Features_Ref)
Rel. | Release |  | IN | COND. | NA | Total | OMITTED
R0 | Read-only pilot & foundations |  | 10 | 0 | 0 | 10 | 0
R1 | India-first unified profit core |  | 62 | 2 | 0 | 64 | 0
R2 | All markets & marketplaces |  | 28 | 4 | 0 | 36 | 4
R3 | Operations |  | 19 | 0 | 0 | 20 | 1
R4 | Pricing automation (conditional) |  | 2 | 3 | 0 | 13 | 8
R5 | Extended operations connectors & clients |  | 7 | 8 | 0 | 16 | 1
— | No release (NA / not applicable) |  | 0 | 0 | 4 | 13 | 9
TOTAL |  |  | 128 | 17 | 4 | 172 | 23
Note: each feature maps to at most one WP; OMITTED features (marketing, v0.3) carry no WP link and no cost; WP-01/02/27–30 carry no features directly (cross-cutting). Connector releases per register: CON-01:R0, CON-02:R1, CON-03:—, CON-04:—, CON-05:R1, CON-06:R1, CON-07:R2, CON-08:R1, CON-09:R1, CON-10:—, CON-11:R2, CON-12:—, CON-13:—, CON-14:—, CON-15:—, CON-16:R2, CON-17:R2, CON-18:R2, CON-19:R5, CON-20:R5, CON-21:R5, CON-22:R5, CON-23:R1, CON-24:—, CON-25:R4, CON-26:—, CON-27:R5, CON-28:R5, CON-29:R2, CON-32:R1, CON-33:R5. Stubs (no release): CON-30, CON-31. Omitted connectors show release '—'.
Note on D44: Hardcoded from scope_register.json (len(features)) at build time

## Features_Ref
Feature extract from scope_register.json v0.3 (172 features; data for Traceability counts) — do not edit
Feature | Domain | Name | Release | Disposition | Calcs | Connectors | WP
F-A01 | A | Login with MFA (authenticator app, e-mail), session policy | R0 | IN |  |  | WP-03
F-A02 | A | Multi-workspace / multi-account switcher | R0 | IN |  |  | WP-04
F-A03 | A | Legal entities, brands, stores, marketplaces, warehouses config | R0 | IN |  |  | WP-04
F-A04 | A | Currencies, timezones, target periods per store | R0 | IN | CALC-026 |  | WP-04
F-A05 | A | Summary dashboard across accounts | R2 | IN | CALC-013,CALC-051,CALC-101 |  | WP-08
F-A06 | A | User invitations & roles by function/product/market | R0 | IN |  |  | WP-03
F-A07 | A | Safe demo mode (synthetic data) | R0 | IN |  |  | WP-03
F-A08 | A | Data retention & lifecycle settings | R0 | IN |  |  | WP-06
F-A09 | A | Personalization: dark/light, remembered views, column pickers | R1 | IN |  |  | WP-08
F-A10 | A | Vendor SaaS billing / subscription | — | NA
F-B01 | B | Profit tiles Today/Yesterday/MTD/Forecast/Last month with comparisons | R1 | IN | CALC-002,CALC-013,CALC-045,CALC-108 | CON-01 | WP-08
F-B02 | B | Tile 'More' P&L drilldown (expandable lines, fee breakdown) | R1 | IN | CALC-001,CALC-003,CALC-010,CALC-012,CALC-015,CALC-019,CALC-050,CALC-051,CALC-052 |  | WP-08
F-B03 | B | Chart view (units/ads/refunds/net profit) with configuration | R1 | IN |  |  | WP-08
F-B04 | B | P&L table by day/month with heatmap and compare/YoY | R1 | IN | CALC-013,CALC-050,CALC-051,CALC-108 |  | WP-08
F-B05 | B | Trends per product per metric with forecast column | R1 | IN | CALC-030,CALC-031,CALC-108 |  | WP-08
F-B06 | B | Map / region view (sales, stock) | R2 | IN | CALC-111 |  | WP-08
F-B07 | B | Products/Order-items tables with group-by, search, sort, column picker, export | R1 | IN |  |  | WP-08
F-B08 | B | Custom dashboard tiles (up to 8 metrics) | R1 | IN |  |  | WP-08
F-B09 | B | Targets, ASP, AOV, sessions/conversion, payout estimate | R1 | IN | CALC-014,CALC-016,CALC-017,CALC-018,CALC-048,CALC-053,CALC-054 |  | WP-08
F-B10 | B | Amazon / Shopify / other-channel dashboard views | R2 | IN |  |  | WP-08
F-B11 | B | Dashboard currency switch | R2 | IN | CALC-026,CALC-081 |  | WP-08
F-C01 | C | COGS policies: fixed, percentage, by period, batch, FIFO, weighted average | R1 | IN | CALC-005,CALC-006,CALC-007,CALC-078 |  | WP-09
F-C02 | C | FIFO oversold policy (last batch / zero / fixed) + alert | R1 | IN | CALC-007 |  | WP-07
F-C03 | C | Landed-cost elements per batch | R1 | IN | CALC-008 |  | WP-09
F-C04 | C | SKU/ASIN/variant mapping, multi-channel COGS tab | R1 | IN | CALC-066,CALC-087 |  | WP-09
F-C05 | C | Bundles / BOM | R2 | IN | CALC-005 |  | WP-09
F-C06 | C | COGS import/export (CSV/XLSX), multi-product batch | R1 | IN |  |  | WP-09
F-C07 | C | Recurring COGS feed from Google Sheets / URL (daily) | R1 | IN | CALC-087 | CON-23 | WP-09
F-C08 | C | Missing/zero COGS detection and alert | R1 | IN | CALC-043 |  | WP-34
F-C09 | C | Cost-change history, preview, closed-period effect | R1 | IN | CALC-024 |  | WP-07
F-D01 | D | Marketplace fee taxonomy incl. India-specific (TDS, affordability, technology, closing) & unknown codes | R1 | IN | CALC-003,CALC-067,CALC-109 | CON-01 | WP-07
F-D02 | D | Refunds: partial, refund-without-return, unsellable, fee/tax reversals | R1 | IN | CALC-004,CALC-009,CALC-053,CALC-054,CALC-082 |  | WP-07
F-D03 | D | Actual vs estimated shipping; ShipStation actuals | R1 | IN | CALC-020 | CON-32 | WP-13
F-D04 | D | Shipping profiles (zones/weight/value/units); highest-vs-sum mixed orders | R1 | IN | CALC-020 |  | WP-13
F-D05 | D | Pick & pack per order/item, first-X-items rate | R1 | IN | CALC-021 |  | WP-13
F-D06 | D | Gateway / POS / payment fees | R1 | IN | CALC-022 | CON-06 | WP-13
F-D07 | D | Indirect expenses: one-off/recurring/daily; multi-marketplace; tag/SKU | R1 | IN | CALC-024 |  | WP-10
F-D08 | D | Variable / tag-based expenses with conditions and validity | R1 | IN | CALC-011,CALC-091 |  | WP-10
F-D09 | D | Fee amortization (daily) for storage/inbound/removal etc. | R1 | IN | CALC-024 |  | WP-07
F-D10 | D | Cross-market allocations & conservation | R1 | IN | CALC-023 |  | WP-07
F-D11 | D | GST/TCS/VAT recoverability & marketplace-facilitator split | R1 | IN | CALC-025 |  | WP-07
F-E01 | E | PPC dashboard portfolio→campaign→ad group→keyword→search term with profit & break-even ACOS | R4 | OMITTED | CALC-028,CALC-029 | CON-02
F-E02 | E | Real ACOS / TACOS product-scoped on trends | R1 | IN | CALC-030,CALC-031 |  | WP-08
F-E03 | E | Bid recommendations, harvesting, negatives, budget adjustments, isolation | R4 | OMITTED | CALC-088,CALC-112 | CON-26
F-E04 | E | Automation: manual approval / autopilot; day parting (beta) | R4 | OMITTED |  | CON-26
F-E05 | E | Automation log completed/pending (repricer writes only) | R4 | IN |  |  | WP-20
F-E06 | E | External ads (Google/Meta/TikTok/Snap/Pinterest/Taboola) spend + UTM/session attribution | R5 | OMITTED | CALC-032 | CON-08..CON-14
F-E07 | E | Amazon Attribution external traffic | R2 | OMITTED | CALC-032 | CON-04
F-E08 | E | Search-term performance (Brand Analytics) | R4 | OMITTED | CALC-074 | CON-03
F-E09 | E | Keyword research | R4 | OMITTED |  | CON-03
F-E10 | E | Product/ad mapping & organic vs paid split | R4 | OMITTED | CALC-031,CALC-049
F-E11 | E | First-party cookie / Shopify customerJourneySummary attribution | R2 | OMITTED | CALC-032 | CON-05
F-F01 | F | LTV per buyer (sales, units, orders) 3/6/12/24 months, per product | R2 | IN | CALC-033 |  | WP-14
F-F02 | F | Cohorts, retention, repeat rate, time-to-second purchase, CAC, payback with maturity flags | R2 | IN | CALC-034,CALC-035,CALC-036 |  | WP-14
F-F03 | F | Repeat customers report (by brand) | R2 | IN | CALC-035,CALC-083 |  | WP-11
F-F04 | F | Subscription contracts vs repeat orders (SnS count observed) | R2 | CONDITIONAL |  | CON-29 | WP-14
F-G01 | G | Inventory by warehouse / fulfillment mode; reserved, saleable, damaged, prep, inbound, ordered | R3 | IN | CALC-040 | CON-01 | WP-15
F-G02 | G | Stock value & age, velocity, days of cover, safety stock, lead time | R3 | IN | CALC-037,CALC-038 |  | WP-15
F-G03 | G | Reorder alerts / action-required with funds needed & profit at risk | R3 | IN | CALC-039 |  | WP-15
F-G04 | G | Purchase orders (draft/ordered/shipped), suppliers (multi-currency), receiving, MOQ/carton | R3 | IN | CALC-039 |  | WP-15
F-G05 | G | FBA / inbound shipment tracking, % received, discrepancies | R3 | IN |  | CON-01 | WP-15
F-G06 | G | Prep-center stock auto-reduction on inbound | R3 | IN | CALC-040 |  | WP-15
F-G07 | G | Stock history report & reconciliation, shrinkage | R3 | IN | CALC-040 |  | WP-15
F-G08 | G | Reseller / sourcing workflow (mobile scan, FNSKU labels) | R5 | CONDITIONAL |  | CON-01 | WP-24
F-H01 | H | Lost & damaged reimbursement candidates (estimate, report) | R3 | IN | CALC-044 | CON-01 | WP-16
F-H02 | H | Returns not received / refund-without-return candidates | R3 | IN | CALC-044 | CON-01 | WP-16
F-H03 | H | FBA fee-change (weight/dimension) candidates | R3 | IN |  | CON-01 | WP-16
F-H04 | H | Claim tracker: eligibility, deadlines, policy version, evidence, appeals, realized credits | R3 | IN | CALC-044 |  | WP-16
F-H05 | H | Review request campaigns: eligibility, targeting, schedules, dedup, per-order status | R3 | OMITTED | CALC-042 | CON-24
F-H06 | H | Alerts: listing/Buy Box/seller count/fee/feedback/stock/ad-spend missing or spike/inbound; priorities; routing; resolution (no PPC recommendation alerts) | R3 | IN | CALC-043 |  | WP-17
F-H07 | H | Alert notification channels (in-app, e-mail, per-recipient) & escalation | R3 | IN |  |  | WP-17
F-H08 | H | Custom buyer follow-up e-mails via Buyer-Seller Messaging | — | NA
F-H09 | H | Alert notification channel in Seller Central | — | NA
F-I01 | I | Repricer strategy profiles (max profit/sales/liquidation), min/max by ROI/margin/COGS+%, floor, overrides | R4 | CONDITIONAL | CALC-041 | CON-25 | WP-22
F-I02 | I | Guardrails: marketplace bounds, ±% caps, stale-data stop, kill switch, simulation, approval | R4 | CONDITIONAL | CALC-041,CALC-075 |  | WP-20
F-I03 | I | Price history, Buy Box observations, change log, provider-result audit | R4 | IN |  | CON-01 | WP-22
F-J01 | J | Walmart / WFS / Connect / SEM views, Walmart-only summary | R2 | IN |  | CON-16 | WP-23
F-J02 | J | eBay dashboard, LTV, products, orders, expenses; order-level COGS import | R2 | IN |  | CON-17 | WP-23
F-J03 | J | TikTok Shop (commerce) distinct from TikTok Ads | R2 | IN |  | CON-18 | WP-23
F-J04 | J | Multichannel fulfillment order filtering & economic dedup (MCF/WFS) | R2 | IN | CALC-047 |  | WP-13
F-J05 | J | Amazon→Shopify listing / MCF connector (historical claim) | R5 | CONDITIONAL |  | CON-05 | WP-23
F-B12 | B | Unified dashboard: Amazon + Shopify + B2B in one tiles/chart/P&L/trends view with channel, account and entity filters | R1 | IN | CALC-101,CALC-050,CALC-051 | CON-01,CON-05 | WP-32
F-B13 | B | Sellerboard-compatible P&L mode (same line names, order and definitions) with contribution-margin toggle | R1 | IN | CALC-050,CALC-051,CALC-052 |  | WP-34
F-B14 | B | Calculation lineage drawer and data freshness/completeness indicators | R1 | IN |  |  | WP-34
F-B15 | B | Targets and budget vs actual by channel/entity | R2 | IN | CALC-107 |  | WP-36
F-B16 | B | Parallel-run reconciliation against Sellerboard exports during migration | R1 | IN | CALC-051 |  | WP-34
F-B17 | B | SnS penetration and BSR snapshot | R1 | IN | CALC-072,CALC-085 | CON-01 | WP-08
F-C10 | C | COGS variants: tiered quantity cost, % of list/selling price, shared COGS master across channels | R1 | IN | CALC-078,CALC-087 |  | WP-09
F-C11 | C | Closing a purchase order creates a cost batch with freight allocation | R3 | IN | CALC-086 |  | WP-15
F-C12 | C | Grade & Resell COGS double-count guard | R1 | IN | CALC-080 |  | WP-07
F-D12 | D | Shopify revenue composition: gross sales, discounts, shipping charged, refunds, tips, chargebacks, gift cards | R1 | IN | CALC-076,CALC-052 | CON-05 | WP-13
F-D13 | D | Payment fees per gateway (platform fee + gateway % + fixed; Auto actual) | R1 | IN | CALC-022 | CON-05,CON-06 | WP-35
F-D14 | D | Return shipping, return processing and country surcharge | R1 | IN | CALC-077 |  | WP-35
F-D15 | D | Order inclusion rules (status/channel/tag) and COD/RTO cost handling | R1 | IN | CALC-090,CALC-104 | CON-05 | WP-35
F-D16 | D | Actual courier/3PL fulfilment cost import replacing profile estimates | R1 | CONDITIONAL | CALC-105 | CON-32 | WP-35
F-D17 | D | Advertising cost composition incl. flagged expenses and local GST on ads | R1 | IN | CALC-079 |  | WP-07
F-D18 | D | Fee allocation: inbound by volume/weight; account-level fees by driver | R1 | IN | CALC-067 | CON-01 | WP-07
F-E12 | E | Dual attribution: platform-reported vs first/last-visit attributed, customer journey | R2 | OMITTED | CALC-061,CALC-056 | CON-05,CON-08,CON-09
F-E13 | E | PPC profit, unit metrics and break-even bid | R4 | OMITTED | CALC-055,CALC-056,CALC-057,CALC-049 | CON-02
F-E14 | E | Day parting (heatmap read; bid writes conditional) | R4 | OMITTED | CALC-058 | CON-26
F-E15 | E | Blended ROAS, POAS, MER | R1 | IN | CALC-059 |  | WP-08
F-E16 | E | Amazon Attribution campaign-level profit | R2 | OMITTED | CALC-060 | CON-04
F-F05 | F | Trailing-window LTV set (3/6/12/24 and 12–48 months) incl. profit per customer, repurchase rate, days between orders, CAC, ROAS, POAS | R2 | IN | CALC-084 | CON-05 | WP-14
F-F06 | F | Replenishment cycle tracking for cartridges/candles with due list | R2 | IN | CALC-106 | CON-05 | WP-14
F-G09 | G | Weighted velocity, seasonality, lead-time components, days until next order, stock value/potential, missed profit, profit forecast | R3 | IN | CALC-037,CALC-038,CALC-039,CALC-062,CALC-063,CALC-064,CALC-065,CALC-089 |  | WP-15
F-G10 | G | Multi-location stock (3PL warehouses, factory, FBA) with shared stock pools | R3 | IN | CALC-092 | CON-05 | WP-15
F-H10 | H | Reimbursement gap, fee-change overcharge, refund-without-return and lost/damaged estimates | R3 | IN | CALC-068,CALC-069,CALC-070,CALC-071 | CON-01 | WP-16
F-H11 | H | Low-inventory-level fee risk alert (weekly, FNSKU) | R3 | IN | CALC-043 | CON-01 | WP-17
F-M01 | M | B2B customer master: distributor/dealer/institution/intercompany, GSTIN, place of supply, terms & limit, price list, salesperson/territory | R1 | IN |  |  | WP-31
F-M02 | M | Manual B2B invoice entry with product master lines, HSN, auto GST split, freight, warehouse/batch; draft → approved → posted (maker-checker) | R1 | IN | CALC-093,CALC-094,CALC-095,CALC-096 |  | WP-31
F-M03 | M | Credit notes, returns, schemes and rebates | R1 | IN | CALC-095,CALC-097 |  | WP-31
F-M04 | M | B2B bulk import (CSV/XLSX) with validation and duplicate detection; accounting export | R1 | IN | CALC-100 |  | WP-31
F-M05 | M | Receivables & collections: receipts, TDS withheld, aging, MSME 45-day flag, DSO, overdue alerts | R2 | IN | CALC-098 |  | WP-31
F-M06 | M | Export invoices (LUT, currency, shipping bill, realisation deadline) | R2 | IN | CALC-099,CALC-026 |  | WP-31
F-M07 | M | B2B in unified dashboard by customer/territory/salesperson with contribution and intercompany elimination | R1 | IN | CALC-097,CALC-100,CALC-101,CALC-110 |  | WP-32
F-M08 | M | Tax masters (HSN/GST rates, LUT, e-invoice/e-way bill settings) and read-only compliance flags | R1 | IN | CALC-102 |  | WP-31
F-M09 | M | Stock deduction on B2B dispatch shared with Shopify/3PL/FBA pools without double count | R2 | IN | CALC-092,CALC-096 |  | WP-31
F-M10 | M | Salesperson commission, price realisation, expected-credit-loss provision | R2 | IN | CALC-103 |  | WP-31
F-M11 | M | Import won deals from the internal B2B lead pipeline as draft invoices (read-only link) | R5 | CONDITIONAL |  | CON-33 | WP-31
F-D19 | D | Ad-spend in R1 profit: Amazon Ads, Google and Meta spend read for the compat Advertising line, blended ROAS/POAS and variable-expense bases | R1 | IN | CALC-079,CALC-059,CALC-091 | CON-02,CON-08,CON-09 | WP-37
F-B18 | B | Period comparisons (Δ, Δ%, previous period, YoY) on tiles, P&L and trends | R1 | IN | CALC-108 |  | WP-08
F-K01 | K | Connector: Amazon SP-API (Orders, Finances, Reports, FBA Inventory, Inbound, Sales, Listings read) | R0 | IN |  | CON-01 | WP-05
F-K02 | K | Connector: Amazon Ads API — spend reporting only (SP/SB/SD v3: spend by campaign, advertised product, day) | R1 | IN |  | CON-02 | WP-37
F-K03 | K | Connector: Amazon Brand Analytics / Search Terms (via Reports API) | — | OMITTED |  | CON-03
F-K04 | K | Connector: Amazon Attribution | — | OMITTED |  | CON-04
F-K05 | K | Connector: Shopify Admin GraphQL (orders, products, inventory, customers L1/L2, fulfillments) | R1 | IN |  | CON-05 | WP-12
F-K06 | K | Connector: Shopify Payments payouts & balance transactions | R1 | IN |  | CON-06 | WP-12
F-K07 | K | Connector: Other payment gateways (Razorpay/PayPal/Stripe) — fee import | R2 | CONDITIONAL |  | CON-07 | WP-23
F-K08 | K | Connector: Google Ads — spend only | R1 | IN |  | CON-08 | WP-37
F-K09 | K | Connector: Meta (Facebook/Instagram) Ads — spend only | R1 | IN |  | CON-09 | WP-37
F-K10 | K | Connector: Microsoft/Bing Ads | — | OMITTED |  | CON-10
F-K11 | K | Connector: TikTok Ads — spend only (for TikTok Shop and Shopify profit) | R2 | CONDITIONAL |  | CON-11 | WP-23
F-K12 | K | Connector: Snapchat Ads | — | OMITTED |  | CON-12
F-K13 | K | Connector: Pinterest Ads | — | OMITTED |  | CON-13
F-K14 | K | Connector: Taboola | — | OMITTED |  | CON-14
F-K15 | K | Connector: Klaviyo | — | OMITTED |  | CON-15
F-K16 | K | Connector: Walmart Marketplace / WFS / Walmart Connect & SEM spend (read) | R2 | IN |  | CON-16 | WP-23
F-K17 | K | Connector: eBay | R2 | IN |  | CON-17 | WP-23
F-K18 | K | Connector: TikTok Shop | R2 | IN |  | CON-18 | WP-23
F-K19 | K | Connector: CJ Dropshipping | R5 | IN |  | CON-19 | WP-39
F-K20 | K | Connector: ShipStation (actual shipping cost) | R5 | IN |  | CON-20 | WP-39
F-K21 | K | Connector: Flexport / SFN | R5 | IN |  | CON-21 | WP-39
F-K22 | K | Connector: Veeqo | R5 | IN |  | CON-22 | WP-39
F-K23 | K | Connector: Private Google Sheets / CSV-XLSX URL feeds (COGS, landed cost, expenses) | R1 | IN |  | CON-23 | WP-09
F-K24 | K | Connector: Amazon Solicitations API (review requests) | — | OMITTED |  | CON-24
F-K25 | K | Connector: Amazon Listings Items (price patch) — repricer writes | R4 | CONDITIONAL |  | CON-25 | WP-22
F-K26 | K | Connector: Amazon Ads write (bids/budgets/negatives) | — | OMITTED |  | CON-26
F-K27 | K | Connector: QuickBooks / Tally export (accounting) | R5 | IN |  | CON-27 | WP-25
F-K28 | K | Connector: Anthropic API (optional explain layer) | R5 | CONDITIONAL |  | CON-28 | WP-26
F-K29 | K | Connector: Subscription provider (Shopify subscription app of record) | R2 | CONDITIONAL |  | CON-29 | WP-23
F-K30 | K | Connector: Courier / 3PL fulfilment cost source (e.g., Eshopbox, courier invoices) — CSV/XLSX first, API discovery | R1 | CONDITIONAL |  | CON-32 | WP-35
F-K31 | K | Connector: Internal B2B lead pipeline app (won deals → draft B2B invoices), read-only | R5 | CONDITIONAL |  | CON-33 | WP-31
F-L01 | L | Reports catalogue: dashboard by day/month/product, orders, sales by product/month, repeat, stock history, COGS, refunds (ads-performance report omitted v0.3) | R1 | IN |  |  | WP-11
F-L02 | L | CSV/XLSX export, scheduled e-mail / private link destinations, permissions | R1 | IN |  |  | WP-11
F-L03 | L | Claude-ready export bundles (schema + data dictionary) | R1 | IN |  |  | WP-11
F-L04 | L | Cashflow (payout-based) & settlement bridge | R5 | IN | CALC-027,CALC-073 | CON-01 | WP-25
F-L05 | L | QuickBooks / accounting export | R5 | IN |  | CON-27 | WP-25
F-L06 | L | Help, glossary, calculation tooltips & lineage | R1 | IN |  |  | WP-08
F-L07 | L | Diagnostics: sync status, freshness, errors, data lineage | R0 | IN |  |  | WP-06
F-L08 | L | Responsive web + mobile PWA; push/offline where feasible | R5 | CONDITIONAL |  |  | WP-24
F-L09 | L | Browser extension (product page profit calc) | R5 | CONDITIONAL |  |  | WP-24
F-L10 | L | Dark/light mode, accessibility (WCAG 2.1 AA), localization (EN; INR/GBP/EUR/USD formats) | R1 | IN |  |  | WP-33
F-L11 | L | Data export/delete (GDPR/DPDP), audit log | R0 | IN |  |  | WP-03
F-L12 | L | Optional AI explain layer (aggregates only) / MCP-style read connector | R5 | CONDITIONAL |  | CON-28 | WP-26
F-L13 | L | Vendor marketing, affiliate pages, branding | — | NA
F-A11 | A | All Amazon marketplaces (NA, EU, FE regions — e.g. US, CA, MX, BR, UK, IE, DE, FR, IT, ES, NL, BE, PL, SE, TR, AE, SA, EG, IN, JP, AU, SG, ZA): marketplace master with currency, timezone, tax regime and fee codes; 'All marketplaces' selector | R2 | IN | CALC-113,CALC-026 | CON-01 | WP-38
F-J06 | J | Walmart / eBay / TikTok Shop fee, settlement and refund mapping into the Sellerboard-compatible P&L lines (unknown fee types → Unclassified + alert) | R2 | IN | CALC-114,CALC-067 | CON-16,CON-17,CON-18 | WP-23
F-J07 | J | Walmart Connect / SEM ad spend as the Walmart Advertising line (spend only) | R2 | IN | CALC-079 | CON-16 | WP-23
F-G11 | G | Walmart WFS inventory and inbound shipments in the inventory planner (Walmart Inventory Planner parity), alongside FBA | R3 | IN | CALC-037,CALC-038,CALC-039,CALC-040 | CON-16 | WP-15
F-A12 | A | Amazon cross-border fulfilment: Pan-EU / EFN and Remote Fulfillment fee codes, pooled FBA stock across marketplaces, stock-transfer flags for VAT | R2 | IN | CALC-067,CALC-092,CALC-113 | CON-01 | WP-38
F-J08 | J | Walmart and eBay report pages (orders, products, daily, monthly) in the reports catalogue | R2 | IN |  | CON-16,CON-17 | WP-23
F-J09 | J | Single source for Walmart Connect / SEM spend per ad account (connector or settlement, never both) | R2 | IN | CALC-079,CALC-114 | CON-16 | WP-23

## Verification
Verification — key totals (live links) — v0.3, cutoff 2026-10-10
All values are formulas linking to the model; LibreOffice recalc via the xlsx skill's recalc.py must report 0 formula errors.
Key total | Value (INR unless stated) | Source cell
Initial bounded release build incl. contingency | 21060305.6367 | Build_Summary!E19
Initial bounded release hours (R0+R1+pro-rata ALL) | 7048.7683 | Build_Summary!B19
Full approved parity build incl. contingency | 33124800 | Build_Summary!E12
Monthly OpEx base — full parity | 495760 | OpEx_Monthly!C24
Monthly OpEx base — initial release (lines ≤R1) | 406200 | OpEx_Monthly!C25
36-month cash TCO — full parity, base | 51622160 | TCO!C22
36-month cash TCO — full parity, low | 41297728 | TCO!B22
36-month cash TCO — full parity, high | 67108808 | TCO!D22
36-month cash TCO — initial release, base | 36333505.6367 | TCO!C16
Build cost incl. contingency — R0 | 5812800 | Build_Summary!E5
Build cost incl. contingency — R1 | 12451200 | Build_Summary!E6
Build cost incl. contingency — R2 | 3816000 | Build_Summary!E7
Build cost incl. contingency — R3 | 3628800 | Build_Summary!E8
Build cost incl. contingency — R4 | 864000 | Build_Summary!E9
Build cost incl. contingency — R5 | 2116800 | Build_Summary!E10
Build cost incl. contingency — ALL | 4435200 | Build_Summary!E11
Total hours (all WPs) | 11180 | WorkPackages!E40
Features in register | 172 | Traceability!D41
Feature→WP links counted | 145 | Traceability!D40
Sellerboard spend (sellerboard.com + .io), monthly | 13104 | Build_vs_Buy!B7
Category total reconciles to full parity | OK — reconciles | Build_Summary!F38
Phased TCO build reconciles | OK — reconciles | TCO!E29
WorkPackages total vs register | OK — matches register 11,180 h | WorkPackages!I40
Traceability feature check | OK | Traceability!D45
Cash TCO includes the 20% contingency as committed budget; it is shown separately in Build_Summary. Regenerated by engineering/build_cost_model.py and verified by LibreOffice recalc (xlsx skill recalc.py) on 2026-10-10.

## Change_v02_v03
Change bridge — v0.2 vs v0.3 (both cutoff 2026-10-10)
v0.2 column = BLUE hardcoded values from the v0.2 workbook (Verification sheet, LibreOffice-recalculated 2026-10-10, incl. the security/landing-zone OpEx line). v0.3 column = live formulas into this model. Assumption values (rates, contingency, OpEx lines, multipliers) are unchanged — differences are scope-driven (marketing omitted; all marketplaces in R2).
A. Key totals
Metric | v0.2 | v0.3 | Δ (v0.3 − v0.2) | Δ % | Note
Total hours (all WPs) | 12000 | 11180 | -820 | -6.833% | −1,220 h marketing (WP-18/19/21 retired, WP-14 −120, WP-20 −80, WP-23 −120) + 400 h new (WP-38, WP-39)
Work packages (count) | 37 | 36 | -1 | -2.703% | 3 retired, 2 added
Programme calendar (weeks, R0–R5) | 64 | 62 | -2 | -3.125% | R2 10→14, R4 10→6, R5 12→10
Initial bounded release — hours | 6969.2308 | 7048.7683 | 79.5375 | 1.141% | R0+R1+pro-rata ALL (pro-rata share changes because R2–R5 hours changed)
Initial bounded release — INR incl. contingency | 20839827.6923 | 21060305.6367 | 220477.9444 | 1.058% | R0/R1 scope unchanged
Full approved parity — INR incl. contingency | 35558400 | 33124800 | -2433600 | -6.844%
Monthly OpEx base — full parity | 470560 | 495760 | 25200 | 5.355% | New ChatGPT/Codex seats line (12 × $25); Ads API line ₹0 (spend read)
Monthly OpEx base — initial release (≤R1) | 381000 | 406200 | 25200 | 6.614% | Includes ChatGPT/Codex seats from R0
36-month cash TCO — full parity, base | 53148560 | 51622160 | -1526400 | -2.872%
36-month cash TCO — full parity, low | 42518848 | 41297728 | -1221120 | -2.872%
36-month cash TCO — full parity, high | 69093128 | 67108808 | -1984320 | -2.872%
36-month cash TCO — initial release, base | 35205827.6923 | 36333505.6367 | 1127677.9444 | 3.203%
Build incl. contingency — R0 | 5812800 | 5812800 | 0 | 0%
Build incl. contingency — R1 | 12451200 | 12451200 | 0 | 0%
Build incl. contingency — R2 | 1540800 | 3816000 | 2275200 | 147.7%
Build incl. contingency — R3 | 4483200 | 3628800 | -854400 | -19.06%
Build incl. contingency — R4 | 2971200 | 864000 | -2107200 | -70.92%
Build incl. contingency — R5 | 3864000 | 2116800 | -1747200 | -45.22%
Build incl. contingency — ALL | 4435200 | 4435200 | 0 | 0%
Features in register | 165 | 172 | 7 | 4.242% | 7 added (F-A11, F-A12, F-G11, F-J06…F-J09); 23 now OMITTED (kept for traceability, not built)
B. Work packages that drove the change
WP — name (v0.3, or v0.2 for retired) | v0.2 hours | v0.3 hours | Δ hours | Δ INR incl. cont. | Driver
(Retired WPs have 0 h in v0.3; their Δ INR uses the v0.2 owner-role rate from Assumptions.)
WP-14 — LTV, repeat customers, cohorts & replenishment cycles (no ad attribution, no campaign analytics) | 340 | 220 | -120 | -345600 | [R2→R2] Reduced 340→220 h: LTV, repeat customers, cohorts & replenishment kept; ad attribution, CAC payback by campaign and Amazon Attribution removed (marketing omitted)
WP-18 — Review requests (Solicitations) — marketing, omitted v0.3 | 200 | 0 | -200 | -624000 | [R3→retired] RETIRED — review-request e-mails (Solicitations) are marketing; omitted by Owner 2026-10-10
WP-19 — Amazon Ads campaign/PPC analytics — marketing, omitted v0.3 (ad spend read stays in WP-37) | 380 | 0 | -380 | -1185600 | [R4→retired] RETIRED — Amazon Ads campaign/PPC analytics omitted; ad SPEND read stays in WP-37 (R1)
WP-20 — Automation safety framework for repricer writes: simulation, maker-checker, canary, kill switch, audit, replay | 360 | 280 | -80 | -230400 | [R3→R3] Reduced 360→280 h: safety framework now serves repricer writes only (no PPC writes)
WP-21 — PPC recommendations & bid/negative automation — marketing, omitted v0.3 | 320 | 0 | -320 | -921600 | [R4→retired] RETIRED — PPC recommendations, bid/budget/negative automation, day parting omitted
WP-23 — Marketplace connectors: Walmart (Marketplace, WFS, Walmart Connect/SEM spend read), eBay, TikTok Shop — orders, fees, settlements, returns, inventory; compat P&L mapping | 720 | 600 | -120 | -374400 | [R5→R2] Moved R5→R2 and re-scoped 720→600 h: Walmart (incl. WFS, Walmart Connect/SEM spend), eBay, TikTok Shop marketplaces only; external-ads & Klaviyo connectors removed; ops connectors split to WP-39
WP-38 — All Amazon marketplaces: NA/EU/FE regions, marketplace master (currency, timezone, tax regime, fee codes), multi-region auth & rate limits, per-marketplace fixtures | 0 | 240 | 240 | 748800 | [new→R2] NEW — all Amazon marketplaces (NA/EU/FE): marketplace master, tax regimes, multi-region auth (R2)
WP-39 — Operations connectors: ShipStation, Flexport/SFN, Veeqo, CJ Dropshipping (read-only) | 0 | 160 | 160 | 499200 | [new→R5] NEW — ShipStation, Flexport/SFN, Veeqo, CJ Dropshipping read connectors split out of WP-23 (R5)
Sum of driver WPs | 2320 | 1500 | -820 | -2433600
Check: Δ hours of drivers = Δ total hours (all other WPs unchanged) |  |  | OK — reconciles
Check: Δ INR of drivers = Δ full parity INR |  |  |  | OK — reconciles
C. Release calendar & hours by release
Release (v0.3 name) | v0.2 weeks | v0.3 weeks | v0.2 hours | v0.3 hours | Comment
R0 — Read-only pilot & foundations | 8 | 8 | 1840 | 1840
R1 — India-first unified profit core | 14 | 14 | 4200 | 4200
R2 — All markets & marketplaces | 10 | 14 | 520 | 1240 | Gained WP-23 (Walmart/eBay/TikTok Shop) and WP-38 (all Amazon marketplaces); WP-14 reduced; +4 weeks
R3 — Operations | 10 | 10 | 1540 | 1260 | Lost WP-18 (review requests); WP-20 reduced
R4 — Pricing automation (conditional) | 10 | 6 | 1000 | 300 | Lost WP-19 and WP-21 (PPC); repricer only; −4 weeks
R5 — Extended operations connectors & clients | 12 | 10 | 1300 | 740 | Lost WP-23 to R2; gained WP-39 (ops connectors); −2 weeks
ALL — cross-cutting |  |  | 1600 | 1600
TOTAL | 64 | 62 | 12000 | 11180
Scope kept on purpose: ad SPEND is still read (WP-37, R1) as the Advertising cost line so net profit matches Sellerboard; LTV and repeat-customer reports stay (WP-14). History: v0.1 (2026-09-10) 10,280 h / ₹3,03,45,600 full parity → v0.2 12,000 h / ₹3,55,58,400 → v0.3 (this model).
Note on B6: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B7: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B8: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B9: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B10: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B11: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B12: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B13: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B14: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B15: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B16: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B17: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B18: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B19: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B20: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B21: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B22: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B23: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B24: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B25: v0.2 value — source: v0.2 06_Cost_and_Traceability_Model.xlsx (Verification / WorkPackages), recalculated 2026-10-10
Note on B30: v0.2: R2 / 340 h
Note on B31: v0.2: R3 / 200 h
Note on B32: v0.2: R4 / 380 h
Note on B33: v0.2: R3 / 360 h
Note on B34: v0.2: R4 / 320 h
Note on B35: v0.2: R5 / 720 h
Note on B36: v0.2: did not exist
Note on B37: v0.2: did not exist
Note on C31: Retired in v0.3
Note on C32: Retired in v0.3
Note on C34: Retired in v0.3